## Exec Summary
Owner | Matt S. | Lam/Lance | Dante B. | Daryl G. | Trevor H. | Daryl G. | Daryl G. | Heidi R. | N/A | Albert/Duri | N/A
Stage | RFQ | PO/Demand Issues | Eng Queue | Material Review | Material Gated | Material In Transit | Started-Wip | At Fair | Complete | Removed from List | Total | Line of Site to Prod. | No Status | Total Count
Stage %
Cum. %
2022-01-28 | [14 empty] | Completion Schedule
[15 empty] | Week Ending | Part Count | % Complete
Daily Snapshot | [14 empty] | 2022-01-15
2022-01-27 | 0 | 26 | 4 | 21 | 10 | 28 | 14 | 3 | 36 | 17 | 159 | 81 | 0 | 159
2022-01-26 | 1 | 23 | 7 | 18 | 10 | 28 | 16 | 3 | 36 | 17 | 159 | 83 | 0 | 159
2022-01-25 | 2 | 22 | 13 | 22 | 5 | 26 | 12 | 5 | 35 | 17 | 159 | 78 | 0 | 159
2022-01-24 | 2 | 13 | 20 | 22 | 6 | 26 | 11 | 10 | 33 | 17 | 160 |  | 0 | 161
2022-01-21 | 2 | 12 | 23 | 21 | 5 | 21 | 22 | 21 | 16 | 17 | 160 |  | 0 | 161
2022-01-20 | 7 | 12 | 31 | 9 | 10 | 16 | 34 | 18 | 7 | 16 | 160 |  | 0 | 161
2022-01-19 | 6 | 9 | 37 | 2 | 34 |  | 31 | 18 | 6 | 15 |  |  | 0
2022-01-18 | 7 | 10 | 37 | 2 | 34 |  | 31 | 18 | 6 | 15 | 160 |  | 0 | 161
2022-01-17 | 6 | 11 | 38 | 2 | 38 |  | 26 | 19 | 5 | 15 | 160 |  | 0 | 161
2022-01-14 | 12 | 16 | 29 | 13 | 31 |  | 25 | 17 | 4 | 14 | 161 |  | 0 | 161
2022-01-13 | 12 | 20 | 29 | 14 | 33 |  | 23 | 16 | 4 | 10 | 161 |  | 0 | 161 | >Q1
2022-01-12 | 19 | 21 | 31 | 22 | 29 |  | 24 | 6 | 2 |  | 154 |  | 7 | 161 | TBD
2022-01-11 | 8 | 9 | 31 | 5 | 20 |  | 20 | 1 | 2 |  | 96 |  | 65 | 161 | CANCEL
2022-01-10 | 4 | 9 | 31 | 0 | 17 |  | 20 | 3 | 0 |  | 84 |  | 0

## MDC Q1 Playbook
Lam Part No | Critical | CE! | Cust Crit | Group# | Site | FAIR PO | FAIR Date | Kickout PO | Status | PRD | Ship Date | Material Clear | NOTES / Material Shortages | Special Process | HW | OW | Q1 Demand
02-424910-00 | NC | Y | N | Group 2 |  | 4700633222 | TBD | 4700633223 | Removed from List |  | TBD | VALIDATED, REMOVED | No Bid |  |  |  | 0 | =VLOOKUP(playbookData
10-127749-00 | NC |  |  | Group 1 | 03 |  | Approved | 4502363322 | Complete | PRD-0495776 | 2022-01-17 |  |  |  |  | X | 11
839-800969-001
10-132464-00 | NC |  |  | Group 2 |  |  | 2022-01-12 | 4502290425 | At Fair | PRD-0484477 | 2022-01-14 | 2022-11-11 | FAI submitted 1/26 |  | X | X | 0
839-084410-003
839-802495-005
839-802752-003
10-136163-02 | NC | Y | N | Group 2 | 03 | 4700631437 | 2022-01-17 |  | Complete | PRD-0494237 | 2022-01-14 | 1-7dg |  |  |  | X | 2
839-144383-001
839-144384-001
10-143501-00 | NC | Y | N | Group 2 | 03 | 4700633224 | 2022-01-13 | 4700633225 | Complete | PRD-0494712 PRD-0494714 | 2022-01-14 | 1-7dg 1-7dg |  |  |  | X | 1
839-068733-001 |  |  |  |  | 07 | [7 empty] | PO needs to be placed with Austin - VC=1051082
715-250179-004
839-052386-002
839-338318-001
10-143502-00 | NC | Y | N | Group 2 |  | 4700633236 | 2022-01-13 |  | Complete | PRD-0495262 | 2022-01-19 | 1-8dg |  |  |  | X | 1
10-143542-00 | NC | Y | N | Group 2 |  | 4700633236 | TBD |  | Started-Wip | PRD-0495270 | 2022-02-04 | 1-9dg | PR-095133 for MDC elbow submitted 1/10, 1/25 waiting ASA |  |  | X | 1
10-145276-06 | NC | Y | N | Group 2 | 03 | 4700631437 | 2022-01-11 |  | Complete | PRD-0494294 | 2022-01-14 | 1-7dg |  |  |  | X | 2
839-065453-001
10-145276-07 | NC | Y | N | Group 2 | 03 | 4700631437 | 2022-01-11 |  | Complete | PRD-0494321 | 2022-01-14 | 1-7dg |  |  |  | X | 2
839-260256-104
839-260256-106
839-276843-004
839-800969-025
839-245903-003 |  |  |  |  | 07 | [7 empty] | PO needs to be placed with Austin - VC=1051082
839-245903-004
839-086299-005
839-294188-001 |  |  |  |  | 07 | [7 empty] | PO needs to be placed with Austin - VC=1051082
839-802321-005
839-084410-005
839-245903-005 |  |  |  |  | 07 | [7 empty] | PO needs to be placed with Austin - VC=1051082
839-253880-003 |  |  |  |  | 07 | [7 empty] | PO needs to be placed with Austin - VC=1051082
839-802506-210
10-146204-00 | NC | Y | N | Group 2 | 03 | 4700631437 | 2022-01-11 |  | Complete | PRD-0494323 | 2022-01-12 | 1-9dg |  |  |  | X | 1
10-149296-00 | NC | Y | N | Group 2 | 03 | 4700633237 | TBD | 4700633453 | Material In Transit | PRD-0494484 PRD-0494671 | 2022-01-31 |  | 1-19dg .125X.028 316L PO-174646 due 1-20 tube service |  |  | X | 7
839-802753-010
839-296543-002 |  |  |  |  | 07 | [7 empty] | PO needs to be placed with Austin - VC=1051082
839-142975-011
839-035038-001
718-A15249-001
839-A05393-001
839-802321-008
839-802495-224
10-149457-00 | NC | Y | N | Group 2 |  | 4700633227 | TBD | 4700633228 | Material Gated | PRD-0495277 PRD-0495278 | TBD |  | 1-26dg 721002 VPD sub PRD-0488549 1-26dg 79-08272-06 need PO |  | X |  | 1
839-088262-116
718-A15249-002
839-802495-223 |  |  |  |  | 07 | [7 empty] | PO needs to be placed with Austin - VC=1051082
839-245714-003
839-802321-901
839-173293-005
839-050771-103
839-069366-813
839-802568-012
839-247059-005
839-232238-131
10-149847-00 | NC | Y | N | Group 2 |  | 4700633237 | TBD |  | Material In Transit | PRD-0495279 | 2022-02-09 |  | 1-13dg GDP00024 PO-174255 due 2-1 windustrl |  |  | X | 1
839-050824-100
839-296130-004
839-142975-012
10-149893-00 | NC | Y | N | Group 2 |  | 4700633237 | TBD |  | Started-Wip | PRD-0495280 | 2022-02-02 | 1-9dg | Eng requested step file from LAM |  |  | X | 1
10-344639-00
839-A37931-001
10-149926-00 | NC | Y | N | Group 2 | 03 | 4700633230 | TBD |  | Started-Wip | PRD-0494675 | 2022-01-14 | 1-7dg |  |  |  | X | 1
839-A07893-102
839-178917-005
10-318747-00
839-142975-014
839-111291-001
839-111291-100
839-273829-101
839-215223-003
839-287911-001
839-245714-006
839-342819-001
839-283987-002 | [12 empty] | PO needs to be placed with Austin - VC=1051082
839-802495-121
839-035359-001
839-253770-004
839-274114-115
839-255335-202
839-272408-191
839-272408-192
853-264802-001 |  |  |  |  | 07 | [7 empty] | PO needs to be placed with Austin - VC=1051082
839-227615-002
839-245412-005
839-245414-005
839-282355-001 |  |  |  |  | 07 | [7 empty] | PO needs to be placed with Austin - VC=1051082
839-296130-002
839-249023-002
839-256781-101
839-258712-101
839-263996-001
853-265069-001
839-052504-101
839-263988-001
839-173304-004
839-263662-640
839-273829-002 |  |  |  |  | 07 | [7 empty] | PO needs to be placed with Austin - VC=1051082
839-270596-002
839-050824-002
839-802706-001
839-247059-004
839-247059-006
839-251638-013
839-253621-002
839-254277-002
839-254630-202
839-255332-101
839-255332-102
839-255335-102
839-255755-014
839-255755-015
839-255755-113
839-255755-211
839-255755-312
839-258707-202
839-262560-002
10-192524-00
718-A15249-003
839-261602-101
839-235063-003
839-235074-003
853-343830-001
839-263662-610
839-197320-001
839-100780-002
839-251846-002
10-150114-00 | NC | Y | N | Group 2 | 03 | 4700633237 | 2022-01-12 |  | Complete | PRD-0495281 | 2022-01-14 | 1-7dg |  |  |  | X | 1
839-188213-001
839-243275-010
715-250174-009
715-250176-009
839-014757-067
839-320032-001
839-237526-003
839-309161-002
839-034096-266
839-190348-001
839-034095-266
839-057594-352
839-272203-306
839-256379-002
857-226166-002
839-191302-001
10-152277-00 | NC | Y | N | Group 2 | 03 | 4700633237 | 2022-01-11 |  | Complete | PRD-0495283 | 2022-01-12 | 1-9dg | shipped, but no FAI submitted to portal |  |  | X | 1
839-336559-101
839-301574-001
839-242397-005
839-242397-008
839-346263-010
10-153142-00 | NC | Y | N | Group 2 |  | 4700633237 | TBD |  | PO/Demand Issues | PRD-0495286 | 2022-02-02 | 1-9dg | At FAI- need 45XXXX PO; no BOM in myLAM 1/6 Eng submitted PR-094960, decision clear but need ASA |  |  | X | 1
839-180954-001
839-184513-001
10-399977-00
715-333376-001
839-315079-030 |  |  |  |  | 07 | [7 empty] | PO needs to be placed with Austin - VC=1051082
839-286202-001
839-339554-014
839-285194-001
839-276771-101
839-251608-005
839-256373-003
839-330300-010
839-256374-003
839-275547-002
839-292540-005
839-292541-006
839-150187-002
839-275705-002
839-080984-716
839-150438-010
839-150439-010
10-156309-00 | NC | Y | N | Group 2 | 03 | 4502379205 | TBD |  | At Fair | PRD-0495287 | 2022-01-20 |  | FAI- Update Jan28 New 4500 PO recieved |  |  | X | 1
10-166680-00 | NC | Y | N | Group 2 | 03 | 4700631437 | 2022-01-12 |  | Complete | PRD-0494300 | 2022-01-14 | 1-8dg |  |  |  | X | 2
10-192524-00 | NC | Y |  | Group 1 | 03 |  | Approved | 4502345948 | Material In Transit | PRD-0487396 | 2022-02-08 |  | 1-25dg 03-10-0148 PO-173574 due 1-25 TALON |  |  | X | 5
839-153046-001
839-150208-001
839-196728-001
839-262574-101
839-288471-001
839-A08509-001
10-255648-00 | NC | Y | N | Group 2 |  | 4700633237 | TBD |  | Material Gated | PRD-0495288 | TBD |  | 1-24dg GDP00524 need PO swaglok, 1/6 Eng submitted PR-094960, decision clear but need ASA |  |  | X | 1
839-A73973-100
839-275359-003
839-015206-001
853-309919-001
839-125459-001
839-125460-001
839-285193-001
10-447301-02
10-447301-01
839-200636-001
10-457066-00
839-010967-201
839-034095-257
839-034096-257
839-106247-050
839-112996-001
839-262885-001
839-801255-015
839-801255-050
10-266070-00 | NC | Y | N | Group 2 | 07 | 4700633230 | TBD | 4700633239 | Started-Wip | PRD-0495056 | 2022-01-27 |  | PO needs to be placed with Austin - VC=1051082 |  | X |  | 3
839-292541-101
839-015124-001
839-293138-003
839-192876-001
839-192908-001
839-288372-001
839-111853-002
839-111854-002
839-112996-002
10-268361-00 | NC |  |  | Group 1 |  |  | Approved | 4502364294 | PO/Demand Issues | PRD-0495809 | 2958465 |  | Per Lam, move forward, and decline cancel on dashboard |  |  | X | 14
10-271203-00 | NC | Y | N | Group 2 | 03 | 4700633237 | 2022-01-11 | 4700633453 | Complete | PRD-0495362 PRD-0495360 | 2022-01-14 | 1-8dg |  |  |  | X | 15
10-271377-00 | NC | Y | N | Group 2 | 03 | 4700633232 | TBD |  | Started-Wip | PRD-0494674 | 2022-01-27 |  |  |  |  | X | 1
839-293138-004
839-275373-003
839-268817-001
839-275376-003
839-275705-004
839-293138-005
839-275384-002
839-210764-006
839-802506-012 |  |  |  |  | 07 | 07 | [6 empty] | PO needs to be placed with Austin - VC=1051082
839-152189-003
839-189665-701
839-228146-001
839-275362-003
839-275365-003
839-275373-002
839-275376-004
839-275384-003
839-275616-002
839-275616-003
839-285193-003
839-286209-001
839-293876-001
839-339554-119
839-A20958-001
839-200744-002
715-A50238-001
715-A50238-002
839-196163-004
839-197320-003
839-200794-002
839-288369-001
839-288370-001
839-288371-001
839-340029-152
10-271948-00 | NC | Y | N | Group 2 | 03 | 4502379205 | TBD | 4700633239 | At Fair | PRD-0495383 PRD-0495381 | 2022-01-17 | 1-8dg | FAI-Update New 4500 PO recieved Jan28 |  |  | X | 15
10-283365-00 | NC | Y | N | Group 2 | 07 | 4700633237 | TBD | 4700633453 | Material In Transit | PRD-0494485 PRD-0494670 | 2022-02-04 |  | 1-19dg 08.0-4000 PO-174661 due 1-28 AMERIFLEX, |  | X |  | 19
839-282487-103
839-274115-101
839-163138-002
839-187802-003
839-192736-001
839-274112-111
839-274114-122
839-280291-002
839-338155-002
839-338175-001
839-339383-002
839-339554-018
839-342759-002
839-343543-005
10-296855-00 | NC | Y | N | Group 2 | 07 | 4700633230 | TBD | 4700633239 | Material In Transit | PRD-0494357 PRD-0494689 | 2022-01-31 |  | 1-19dg 7W-250 transfer done 1-19 dg 2WC-250 transfer done |  | X |  | 14
839-197240-004
839-338168-002
10-297758-00 | NC | Y | N | Group 2 |  | 4700633230 | TBD | 4700633239 | Material Gated | PRD-0495388 PRD-0495389 | TBD |  | 1-25dg 79-08272-06 need PO | EP | X |  | 3
839-A06629-004
839-262885-701
10-360075-00
839-201194-006
839-302293-001
839-335367-002
839-336465-002
839-337117-002
839-A15931-001
839-293138-001
839-197320-002
839-215228-003
839-230102-006
839-293138-002
839-339568-002
839-480111-003
839-A38742-003
839-212634-003
839-242887-004
839-088262-216
839-088262-316
839-260256-017
853-288953-011
839-245665-022
839-254274-007
839-308908-001
839-801274-016
839-A24421-001
839-802753-021
839-199810-002
839-212452-001
839-212628-902
839-212634-902
839-212637-922
839-320031-003
839-333540-001
839-333541-001
839-339134-002
839-A14427-907
839-A26168-111
839-A31773-001
839-251608-023
10-452591-00
10-463552-00
839-043660-003
839-043661-003
839-043662-003
839-159432-006
839-198015-002
839-228146-701
839-242382-101
839-243491-501
839-251608-022
839-275359-701
839-275362-701
839-275365-703
839-275373-701
839-275373-702
839-275376-703
839-275376-704
839-275384-701
839-275384-702
839-275536-703
839-275616-701
839-275616-702
839-275705-702
839-275705-704
839-285193-701
839-285193-703
839-286202-701
839-286209-701
853-309919-002
839-A00381-015
839-286557-002
839-232621-001
839-295544-001
839-295549-001
839-310907-002
839-017587-045
839-179586-002
839-286556-003
839-222953-001
839-221761-002
839-240035-002
839-258640-001
839-276985-001
839-338159-001
839-A21962-001
839-A28221-001
839-A32503-001
839-A34682-001
839-204897-001
839-340404-004
839-203931-003
839-221895-001
839-221912-002
839-242887-003
839-283394-004
839-800969-101
839-A04566-001
839-A04694-001
839-229897-001
839-347997-001
839-A24627-321
839-145072-042
839-150185-002
839-150188-002
839-153234-002
839-208223-001
839-208224-001
839-208228-001
839-214456-001
839-307103-002
839-A25965-001
853-A57764-100
839-A38742-004
839-145072-041
839-209340-001
839-210100-001
839-212453-001
839-216850-001
839-216850-002
839-217173-001
839-249915-004
839-283394-003
839-331341-001
839-331341-002
839-340029-151
839-234964-012
839-270967-001
839-125139-601
839-234964-011
839-234964-013
839-234966-013
839-234966-014
839-234966-016
839-288720-701
839-328696-001
839-128843-001
839-A25965-002
839-A32318-001
839-128843-010
839-207747-004
839-229144-003
839-244457-002
839-244459-002
839-244510-002
839-276862-001
839-276864-001
839-277021-001
839-286595-003
839-293876-002
839-326980-011
839-A34410-024
853-A57768-100
839-339825-012
839-159432-002
839-240035-001
839-283878-005
839-285646-003
853-A57766-100
10-297760-00 | NC | Y | N | Group 2 | 03 | 4502379205 | TBD |  | At Fair | PRD-0494305 | 2022-01-14 | 1-9dg | FAI-Update Jan28 New 4500 PO recieved |  |  | X | 3
10-342125-00 | C4 | Y | N | Group 2 |  |  | TBD |  | Removed from List |  | TBD | VALIDATED, REMOVED | Lam resolved with non-MDC supplier |  |  |  | 0
10-343125-00 | NC | Y |  | Group 1 |  |  | Approved | 4502367239 | Material Review |  | TBD |  | Brand new PO 1/10 |  | X |  | 63
839-801274-015
839-A32102-310
839-173293-006
10-400916-00
10-399978-00
10-403704-00
10-403980-00
10-403982-00
839-217638-003
839-228071-001
839-285386-004
839-298050-001
839-335499-102
839-341882-013
839-341882-014
839-A12968-001
839-A24686-010
839-A24686-011
839-A25965-003
839-A36690-001
857-342816-001
857-343102-001
10-374386-00 | NC | Y | N | Group 2 | 03 | 4700630667 | TBD | 4502349377 | Material In Transit | PRD-0493004 | 2022-02-04 |  | 1-18dg 10-374386-00-01 PO-174615 due 1-27 A&T LT 20 days |  |  | X | 55
839-289794-002
16-342555-00 |  |  |  |  | 07 | [7 empty] | PO needs to be placed with Austin - VC=1051082
839-347996-001
839-183524-001
839-183530-001
839-183532-001
839-183535-001
839-183536-001
839-183538-001
839-240036-001
839-347998-003
839-A20409-195
853-A57757-100
10-394919-00 | C4 |  |  | Group 2 |  | 4700625847 | TBD |  | Started-Wip | PRD-0488385 | 2022-01-26 | [5 empty] | 10
10-398119-00 | C1 |  |  | Group 1 |  |  |  |  | PO/Demand Issues |  | TBD |  | Open orders (22pcs) with UCT and Texon. Need Lam input. |  |  |  | 0
10-410634-00 | NC |  |  | Group 2 |  | 4700625847 | TBD |  | Removed from List |  | TBD | VALIDATED, REMOVED | 1/17 Eng submitted PR-095664 1/18 PR rejected - Cancel |  |  |  | 11
839-A20409-704
853-344013-001
839-A57590-100
10-456237-00
839-144006-001
839-174226-003
839-183533-001
839-183537-001
839-247059-101
839-250405-001
839-254632-202
839-256375-003
839-256378-002
839-256379-004
839-262560-001
839-320026-001
839-320028-001
839-320030-001
839-320552-001
839-A06629-002
839-A20409-193
853-A30073-009
10-413657-00 | C4 | Y | N | Group 2 |  | 4700633230 | TBD | 4700633239 | Material In Transit | PRD-0495393 PRD-0495394 | 2022-03-03 |  | 1-24dg 10-413657-00-2 PO-174895 due 2-23 A.R. MACHINING, LT 15 days 1-24 dg 11.00-1600 PO-175001 due 2-16 AMERIFLEX, 70 day LT |  | X |  | 91
839-810303-001
839-194463-001
839-229279-001
839-229665-001
839-320026-005
839-320028-005
839-320030-005
839-320045-005
839-320552-005
839-341189-002
839-A05845-010
839-A06053-021
839-A20409-499
839-A23002-008
839-A29488-009
839-A32729-001
853-A24821-007
839-A24405-002
839-045389-001
839-182332-001
839-215223-004
839-242364-002
839-242365-002
839-A06629-001
839-A09056-121
839-A09056-231
839-A20409-018
839-A20409-063
839-A20409-076
839-A20409-161
839-A20409-180
839-A20409-192
839-A20409-197
839-A20409-271
839-A20409-278
839-A20409-375
839-A20409-394
839-A20409-400
839-A20409-711
839-A22789-020
839-A24195-001
839-A31145-005
839-A34450-412
839-A42176-012
839-A50147-001
839-A57591-100
839-A62703-001
10-417717-00 | NC | Y |  | Group 1 |  | 4502367387 | TBD | 4502367387 | Material Review | PRD-0498597 | TBD |  | 1-25dg 10-417717-00-02 need PO PROTRACK PRECISION |  |  |  | 53
839-285520-002
839-286560-006
839-A22789-003
839-A23002-002
853-A27636-001
853-291271-003
10-384833-00
10-385324-00
10-385567-00
839-088262-114
839-284019-002
839-286146-002
839-286561-002
839-286562-002
839-286564-002
839-286565-002
839-286597-002
839-287739-003
839-294186-006
839-294186-007
839-294186-008
839-298115-001
839-312345-002
839-312361-002
839-328053-002
839-328056-002
839-A13722-001
839-A13722-002
839-A23799-005
839-A24195-004
839-A26133-002
839-A62706-001
853-A08455-200
853-A30072-005
10-418403-00 | C4 | Y | N | Group 2 | 03 | 4700633230 | 2022-01-10 | 4700633239 | Complete | PRD-0495396 PRD-0495397 | 2022-01-11 | 1-7dg PRD-0495397 at FAIR | for PRD-0495396 1-8dg 6LV-8-VCR-3S-8TB3 PO-174427 need confrmd swaglok |  |  | X | 91
10-422851-00 | NC | Y | N | Group 2 | 03 | 4700633230 | TBD | 4700633239 | Material In Transit | PRD-0495055 PRD-0495398 | 2022-02-02 |  | 1-20dg 6LV-2MW-9 due 1-26 swaglok |  |  | X | 29
839-A23799-002
839-A40441-003
10-401908-00
10-403918-00
10-412218-00
10-412291-00
839-157616-002
839-211904-001
839-216498-002
839-217896-005
839-217897-004
839-217898-004
839-217901-003
839-230102-005
839-232283-003
839-286152-002
839-A22789-019
839-A23799-001
839-A23799-003
839-A57594-100
839-A68985-002
853-344013-003
10-422993-00 | NC | Y | N | Group 2 |  | 4700633230 | TBD | 4700633239 | Material In Transit | PRD-0495649 PRD-0496055 | 2022-02-02 |  | 1-20dg 6LV-2MW-9 due 1-26 swaglok |  |  | X | 29
10-422994-00 | NC | Y | N | Group 2 |  | 4700633230 | TBD | 4700633239 | Material In Transit | PRD-0495652 PRD-0496057 | 2022-02-02 |  | 1-20dg 6LV-2MW-9 due 1-26 swaglok |  |  | X | 29
839-312206-002
839-327915-001
839-327760-001
839-326980-012
796-010866-001
839-329649-004
839-A41308-002
10-440913-00
839-275362-004
839-A57595-100
839-A40441-004
10-378252-00
719-200512-001
790-233019-900
839-005525-001
839-014837-001
839-014838-001
839-024694-002
839-078234-100
839-086299-008
839-166332-002
839-217896-925
839-217898-924
839-227093-900
839-227133-900
839-227615-022
839-251846-001
839-270450-916
839-275359-011
839-285733-005
839-286720-001
839-326980-005
839-326980-014
839-326980-021
839-327755-001
839-327784-001
839-328889-001
839-441679-002
839-443242-001
839-802784-100
839-A05130-081
839-A05393-007
839-A13273-004
839-A22789-011
839-A23002-003
839-A24694-004
839-A25634-001
839-A26133-003
839-A26643-002
839-A26645-002
839-A27774-013
839-A27774-014
839-A28802-001
839-A28804-002
839-A28805-002
839-A34410-131
839-A34410-332
839-A34410-334
839-A38283-001
839-A38283-003
839-A61051-001
839-333435-004
839-A24694-001
839-A27945-002
839-A23799-004
839-A23002-009
10-439210-00
839-003422-003
839-005516-002
839-080894-012
839-080894-015 |  |  |  |  | 07 | [7 empty] | PO needs to be placed with Austin - VC=1051082
839-152927-024
839-173298-004
839-175804-700
839-179101-005
839-192679-108
839-199417-003
839-203451-001
839-249824-105
839-258640-002
839-260791-002
839-270961-001
839-283106-001
839-283158-002
839-296813-004
839-302802-001
839-304299-007
839-306501-001
839-308302-001
839-308345-001
839-316509-001
839-316510-001
839-333435-001
839-333435-002
839-333435-003
839-333435-005
839-346288-003
839-A08454-007
839-A09056-046
839-A11803-005
839-A22789-004
839-A22789-012
839-A23002-010
839-A24195-002
839-A24195-003
839-A24195-005
839-A24195-010
839-A24195-019
839-A24686-001
839-A24686-003
839-A24686-004
839-A24686-005
839-A24686-006
839-A24686-007
839-A24686-008
839-A24686-009
839-A24694-002
839-A24694-003
839-A24694-005
839-A24694-009
839-A25040-001
839-A25040-002
839-A25040-003
839-A25040-020
839-A25107-004
839-A25107-005
839-A25107-006
839-A25107-007
839-A25107-008
839-A25107-009
839-A25107-010
839-A26133-001
839-A27945-001
839-A29385-004
839-A29912-001
839-A29912-002
839-A29912-003
839-A29912-004
839-A29912-008
839-A41194-011
839-A41194-012
839-A41308-004
839-A54019-001
839-A57419-100
839-A57596-100
839-A57597-100
839-A57599-100
10-423531-00 | NC | Y | N | Group 2 | 03 | 4700633232 | TBD | 4700633239 | PO/Demand Issues | PRD-0495677 PRD-0495678 | 2022-02-01 |  | At FAI- need 45XXXX PO 1-19dg 6LVV-DPBW4-P-C PO-175462 due 1-19 swaglok |  |  | X | 24
10-430901-00 | NC | Y | N | Group 2 |  | 4700633150 | TBD | 4502358182 | Material Review | PRD-0496097 | TBD |  |  |  | X |  | 15
10-434785-00 | NC | Y | N | Group 2 |  | 4700633232 | TBD | 4700633239 | Material In Transit | PRD-0496061 PRD-0496062 | 2022-02-17 |  | 1-17dg 2.00X.065 304L PO-173427 due 2-9 windustrl | EP | X | X | 22
10-440436-00 | NC |  |  | Group 2 |  | 4700625847 | TBD |  | Material Review | PRD-0498732 | TBD | [5 empty] | 7
10-441091-00
10-441495-00
839-016641-002
839-173304-008
839-247059-102
839-247059-103
839-251315-003
839-255755-116
839-258707-204
839-266166-013
839-801274-005
839-803110-001
839-A24196-002
839-A24196-003
839-A24451-003
839-A24550-004
839-A24550-005
839-A24550-007
839-A24550-013
839-A24550-101
839-A24664-012
839-A24664-014
839-A28212-003
839-A28243-003
839-A31376-002
839-A31611-002
839-A58054-001
839-A58914-306
839-A62160-004
853-A68590-001
839-054297-211
839-054297-213
839-A08598-002
839-294567-001
839-277034-003
839-000110-002
839-178363-001
839-192909-001
839-236754-001
839-256194-001
839-262560-006
839-270436-006
839-270450-002
839-270596-005
839-276986-002
839-285646-004
839-294059-001
839-310538-001
839-310539-001
839-330116-416
839-344471-002
839-A08036-002
839-A12450-025
839-A12452-025
839-A20409-176
839-A27818-002
839-A36574-001
839-A36575-002
839-A54272-002
839-A54278-001
839-A58913-306
853-314281-034
839-A31678-001
839-A31672-001
839-184506-001
839-034096-262
839-152927-026
839-180694-001
714-043308-003
714-048021-001
714-048022-001
839-000173-002
839-029721-003
839-034095-262
839-104808-001
839-152927-025
839-200282-001
839-200282-002
839-210925-012
839-220717-002
839-223386-007
839-277033-001
839-277033-002
839-277033-003
839-277033-004
839-277034-001
839-277034-002
839-277034-004
839-343328-002
839-343329-002
839-348833-004
839-802753-002
839-A01330-001
839-A01340-001
839-A12875-025
839-A12876-025
839-A16840-012
839-A16840-013
839-A20409-701
839-A21661-032
839-A21663-032
839-A25903-001
839-A25903-002
839-A25903-003
839-A25903-004
839-A27582-001
839-A27582-002
839-A28173-001
839-A33982-004
10-445720-00 | NC |  |  | Group 2 |  | 4700625847 | TBD |  | Material Gated | PRD-0493222 | 2022-02-04 |  | 1-26dg 10-445720-00-BEND NC-0008423 |  |  |  | 14
15-431862-00 | C4 |  |  | Group 2 |  | 4700625847 | TBD |  | Removed from List |  | TBD | VALIDATED, REMOVED | No cannot build |  |  |  | 0
16-421995-00 | NC | Y | N | Group 2 |  | 4700633236 | TBD | 4700633452 | Removed from List |  | TBD | VALIDATED, REMOVED | No Bid, Copper |  |  |  | 0
16-421995-00 | NC | Y |  | Group 2 |  |  | TBD |  | Removed from List |  | TBD | VALIDATED, REMOVED | No Bid copper |  |  |  | 0
19-047653-00 | C4 | Y | N | Group 2 |  |  | TBD |  | Material Gated | PRD-0498524 | TBD |  | PO pending per Albert 1/12/22 (vapor degrease) 1-26dg B-KF50-35; PO-175738 not confirmed; COMPUVAC |  |  |  | 310
718-A15249-001 | NC |  |  | Group 1 |  | 4502341622 | TBD | 4502341622 | Material Gated | PRD-0489921 PRD-0489922 | TBD |  | 1-25dg 08T3863860-0028 50.00 (PO-171618 need confrmd MOTION & FLOW (Parker) |  |  |  | 13
839-004572-155 | CV | Y | N | Group 2 |  |  | TBD |  | Removed from List |  | TBD | VALIDATED, REMOVED | Lam resolved with non-MDC supplier |  |  |  | 0
839-068732-006 | CV | Y | N | Group 2 | 03 | 4700634099 | TBD | 4700634156 | PO/Demand Issues | PRD-0495276 | 2022-01-24 | 1-7dg | At FAI- need BOM in LAM portal; MDC CSR contacted |  |  | X | 673
839-221762-103
839-221899-101
839-A13273-005
839-266563-001
839-266563-002
839-311844-202
839-A47949-010
10-341126-00
10-341127-00
10-357282-00
10-451595-00
839-008603-002 |  |  |  |  | 07 | [7 empty] | PO needs to be placed with Austin - VC=1051082
839-026936-001
839-078235-100
839-078236-101
839-109026-001
839-117258-008
839-117258-009
839-158745-006
839-159432-005
839-163138-004
839-163724-101
839-163729-131
839-163729-132
839-163729-133
839-163729-134
839-173951-001
839-175481-001
839-181914-001
839-181934-001
839-181943-001
839-181948-002
839-182736-001
839-183139-001
839-183141-001
839-196491-001
839-196492-001
839-196493-001
839-196494-001
839-197381-002
839-202026-001
839-202213-001
839-214285-001
839-214286-001
839-216497-022
839-220717-101
839-221770-101
839-244457-001
839-248282-003
839-248339-003
839-252507-002
839-260497-001
839-265226-001
839-266685-003
839-268599-001
839-270436-001
839-270450-001
839-270671-300
839-279627-001
839-279629-001
839-279630-001
839-310868-101
839-310868-102
839-310869-101
839-310871-101
839-311279-103
839-330116-415
839-331163-001
839-A07893-107
839-A08036-001
839-A08350-001
839-A15727-001
839-A15730-002
839-A31145-021
839-A31145-022
839-A39668-001
839-A39669-001
839-A39858-002
839-A39907-002
839-A40468-001
839-A40961-001
839-A47826-001
853-031758-001
857-A49227-005
839-069366-808 | CV | Y | N | Group 2 | 03 | 4700634099 | TBD | 4700634157 | At Fair | PRD-0495274 | 2022-01-25 |  |  |  |  | X | 705
839-078004-111 | CV | Y |  | Group 2 |  | 4700633748 | TBD | 4700633749 | Material Review | PRD-0499151 PRD-0499161 | TBD |  | PRD-0499161 Complete Issue with "Size" working with Tony & Pravin PRD-0499151 Scheduled |  |  |  | 673
839-078004-112 | CV | Y |  | Group 2 |  | 4700633748 | TBD | 4700633749 | Material Review | PRD-0499152 PRD-0499153 | TBD |  | PRD-0499153 Complete Issue with "Size" working with Tony & Pravin PRD-0499152 Scheduled |  |  |  | 343
839-078004-911 | C4 | Y |  | Group 2 |  |  | TBD |  | PO/Demand Issues |  | TBD |  | Waiting on PO, quote subbmitted |  |  |  | 129
839-A65300-001
10-029562-00
839-298271-002
839-A43747-001
10-127749-00
10-362208-00
10-367651-00
10-387530-00
10-394792-00
715-240428-003
715-240430-003
715-240431-003
718-337159-001
718-337160-001
718-337646-001
839-016784-002
839-104808-010
839-125230-001
839-161246-004
839-166319-001
839-193406-003
839-199596-002
839-207747-002
839-212452-002
839-215223-005
839-229144-002
839-242334-002
839-244459-001
839-244510-001
839-265412-001
839-265413-001
839-265414-001
839-288471-011
839-288471-014
839-292359-003
839-293396-001
839-295014-001
839-297540-001
839-298288-002
839-299211-003
839-301477-001
839-301645-001
839-305236-011
839-305236-012
839-306088-001
839-306199-002
839-306429-001
839-306674-002
839-326540-002
839-326540-501
839-326540-502
839-326540-503
839-326540-504
839-326540-506
839-326540-508
839-326540-509
839-326540-511
839-326540-512
839-330034-100
839-A31306-002
839-A47445-002
839-A58430-001
839-A65617-001
853-305428-003
853-305428-004
853-305491-003
839-078339-003 | NC |  |  | Group 1 |  |  | TBD | 4502364742 | Removed from List |  | 2958465 | VALIDATED, REMOVED | Recieved cancel confirmation - Albert Khaw - 1/17/22 |  |  |  | 11
839-084411-001 | CV | Y | N | Group 2 | 03 | 4700634099 | 2022-01-10 | 4700634158 | At Fair | PRD-0495282 | 2022-01-11 | 1-7dg |  |  |  | X | 600
839-084412-799 | CV | Y |  | Group 2 |  | 4700633748 | TBD | 4700633749 | Material Gated | PRD-0497999 PRD-0498000 | TBD |  | RFQ submitted 1/17/22 - PO still reflects penny PO 1-26dg PRD-0498000 at estimated 1-26dg 785-038650-004 need PO SINE-TIFIC SOLUTIONS, INC. 1-26dg 101-MPC105 need Po |  |  |  | 151
839-101870-902 | C4 | Y | N | Group 2 | 03 | 4700634099 | TBD | 4700634159 | Material In Transit | PRD-0495291 | 2022-02-08 |  | 1-24dg 839-101870-902-2 PO-174811 due 1-31 AR |  | X | X | 187
839-086686-101
839-A79406-005
10-165803-00
10-343343-00
10-400577-00
10-462628-00
10-465403-00
839-009886-002
839-024692-005
839-054297-632
839-084410-130
839-168291-001
839-172102-001
839-172617-001
839-172777-001
839-174387-001
839-174711-005
839-184409-001
839-184513-004
839-198965-001
839-204407-001
839-214266-001
839-214976-003
839-215223-014
839-217174-001
839-218967-004
839-218967-005
839-221343-005
839-224615-004
839-225084-005
839-245350-003
839-248469-016
839-262413-002
839-275824-712
839-281201-103
839-281203-001
839-281204-121
839-281208-103
839-281209-001
839-290917-001
839-292184-001
839-293408-001
839-294059-002
839-308909-012
839-314286-107
839-329725-002
839-329726-002
839-329847-002
839-339823-450
839-802495-050
839-A03783-010
839-A06868-001
839-A13273-003
839-A13273-006
839-A13273-007
839-A16668-001
839-A16668-002
839-A20954-001
839-A21101-004
839-A31142-002
839-A31143-002
839-A47173-001
839-A50362-002
839-A50366-001
839-A50367-001
839-A50368-002
839-A50371-001
839-A50373-002
839-A50374-001
839-A50375-002
839-A50376-002
839-A54018-001
839-A54027-001
839-A54269-002
839-A54270-002
839-A54271-002
839-A54273-001
839-A54274-001
839-A54276-001
839-A54277-002
839-A54279-001
839-A54280-002
839-A54284-001
839-A54289-001
839-A54500-002
839-A61937-001
839-A64146-001
839-A64147-001
839-A64149-001
839-A64151-001
839-A64154-001
839-A79406-002
853-249210-002
853-A50092-001
839-114189-010 | CV | Y | N | Group 2 | 03 |  | TBD |  | Removed from List |  | TBD | VALIDATED, REMOVED | Lam resolved with non-MDC supplier |  |  |  | 0
839-151213-001 | C4 |  |  | Group 2 |  | 4700632352 | TBD |  | Started-Wip | PRD-0493460 | 2022-01-18 | 1-11dg |  |  |  |  | 1
839-152731-001 | C4 |  |  | Group 2 |  | 4700625847 | TBD |  | Started-Wip | PRD-0494090 | 2022-01-29 | [5 empty] | 16
839-153177-001 | NC | Y | N | Group 2 | 03 | 4700630851 | 2022-01-12 | 4502349964 | Complete | PRD-0492266 | 2022-01-14 | 1-7dg |  |  |  | X | 33
839-155217-002 | C4 | Y | N | Group 2 | 03 | 4502379205 | 2022-01-10 | 4700633239 | At Fair | PRD-0494475 | 2022-01-11 | 1-8dg | FAI - Update Jan28 New 4500 PO recieved |  |  | X | 50
839-166327-002 | NC |  |  | Group 1 |  |  | Approved | 4502364305 | Started-Wip | PRD-0496052 | 2022-01-18 | 2022-01-12 |  |  |  |  | 2
839-173298-003 | NC | Y | N | Group 2 |  | 4700633237 | TBD | 4700633453 | Material In Transit | PRD-0497400 PRD-0497401 | 2022-02-11 |  | Pricing updated in PO 1-26dg 839-173298-003-5 PO-175597 due 2-2 MOSS |  |  |  | 58
839-179096-001 | NC |  |  | Group 2 |  | 4700625847 | TBD |  | Removed from List |  | TBD | VALIDATED, REMOVED | No Bid No Supplier for Aluminum Bends |  |  |  | 0
839-179097-001 | NC |  |  | Group 2 |  | 4700625847 | TBD |  | Removed from List |  | TBD | VALIDATED, REMOVED | No Bid No Supplier for Aluminum Bends |  |  |  | 0
715-023824-002
839-008137-001
839-269017-001
839-314848-002
839-340046-001
839-350020-001
839-A20501-420
839-A47175-001
02-302345-00
10-132464-00
10-145388-00
10-145524-00
10-166693-00
10-449739-00
715-023819-002
715-023820-002
715-023822-001
715-023823-002
715-A43640-001
715-A43640-002
718-108996-001
839-005516-001
839-015127-002
839-024693-005
839-033651-012
839-048241-001
839-069366-814
839-072888-112
839-076157-113
839-080894-065
839-107661-101
839-112996-003
839-160853-001
839-179808-001
839-182332-002
839-184072-002
839-188213-011
839-216497-013
839-216497-016
839-217748-001
839-220717-001
839-220717-003
839-225084-004
839-228766-017
839-228766-101
839-230384-101
839-230386-001
839-230387-002
839-257321-401
839-257321-402
839-258663-010
839-262413-032
839-277661-002
839-288472-001
839-288473-001
839-288474-001
839-288569-001
839-288581-001
839-288820-001
839-288820-002
839-297268-003
839-297834-001
839-298686-002
839-311901-001
839-312373-002
839-317125-604
839-350039-110
839-360028-001
839-360142-910
839-470482-002
839-A00599-003
839-A02063-016
839-A02065-016
839-A03791-003
839-A27818-020
839-A32445-001
839-A33164-002
839-A33165-002
839-A47171-001
839-A47174-001
839-A53544-001
839-A53550-001
839-A54282-002
839-A60685-002
839-A64444-001
839-A67201-001
853-A24821-006
853-A43065-002
839-179101-002 | C4 | Y | N | Group 2 | 03 | 4502379205 | TBD | 4700633452 | At Fair | PRD-0495319 | 2022-01-24 |  | FAI-Update - Jan New 4500 PO recieved;At FAI- need 45XXXX PO PRD-0495020 1-7dg PRD-0495319 ;GDP01339 PO-174857 due 1-11 swaglok 1-7dg PRD-0495020 GDP00497 PO-174879 due 1-12 swaglok 1-7dg PRD-0495020 GDP01339 PO-174857 due 1-21 swaglok 1-7dg PRD-0495020 SS-2-VCR-1 PO-172597 due 1-10 swaglok 1-7dg PRD-0495020 SS-2-VCR-1 PO-172597 due 1-26 swaglok |  |  | X | 34
839-181110-002 | C4 |  |  | Group 2 |  | 4700625847 | TBD |  | Complete | PRD-0494092 | 2022-01-24 |  | Shipped, but no FAI submitted to portal |  |  |  | 36
839-198970-003 | NC |  |  | Group 2 |  | 4700625847 | TBD |  | Material Review |  | TBD |  | Repeat |  |  |  | 6
839-204868-001 | C4 | Y |  | Group 2 |  | 4700633750 | TBD | 4700633751 | Material In Transit | PRD-0497402 PRD-0497403 | 2022-03-23 |  | 1-24dg 839-204868-001-1 PO-175434 due 3-16 A&T |  |  |  | 185
839-204868-003 | C4 | Y | N | Group 2 |  | 4700633232 | TBD | 4700633452 | Material In Transit | PRD-0495284 x5 PRD-0495285 x127 | 2022-02-07 |  | 1-24dg 839-204868-003-A01 PO-174915 due 1-31 B2 machining |  | X | X | 182
839-216850-101 | NC |  |  | Group 1 |  |  |  |  | Removed from List |  | TBD | VALIDATED, REMOVED | No PO on dashboard, PO week of 1/17 |  |  |  | 0
839-221767-001 | C4 |  |  | Group 2 |  | 4700625847 | TBD |  | Complete | PRD-0494093 | 2022-01-19 |  | Shipped, but no FAI submitted to portal |  |  |  | 24
839-229197-001 | NC | Y | N | Group 2 |  | 4700633150 | TBD | 4502358182 | Complete | PRD-0496609 | 2022-01-28 | [5 empty] | 13
839-229542-002 | NC | Y | N | Group 2 |  | 4700630672 | TBD | 4502349967 | Material In Transit | PRD-0492711 | 2022-02-04 |  | 1-24dg 839-229542-002-1,4,5 PO-174615 due 1-27 A&T |  | X | X | 22
839-239359-003 | NC | Y | N | Group 2 |  | 4700633232 | TBD | 4700633452 | Material In Transit | PRD-0494720 | 2022-02-02 |  | 1-26dg 839-239359-003-COIL PO-174900 due 1-27 Capital bend |  |  | X | 21
839-245596-001 | NC | Y | N | Group 2 | 03 | 4700633237 | 2022-01-12 | 4700633453 | Complete | PRD-0494759 PRD-0494916 | 2022-01-17 | 1-7dg 1-7dg |  |  |  | X | 3
839-261436-020 | NC |  |  | Group 1 |  |  | Approved | 4502364312 | Complete | PRD-0496054 | 2022-01-18 | 2022-01-12 |  |  |  |  | 1
839-261436-030 | NC |  |  | Group 1 |  |  | Approved | 4502364328 | Complete | PRD-0496060 | 2022-01-13 | [5 empty] | 1
839-261436-035 | NC |  |  | Group 1 |  | 4502364340 | TBD | 4502364340 | PO/Demand Issues |  | 2958465 |  | Per Lam, move forward, and decline cancel on dashboard |  |  |  | 3
839-336389-652
839-250269-001
10-116652-01
10-132465-00
10-362209-00
10-371663-00
10-383620-00
10-383915-00
10-385179-00
10-385279-00
10-385550-00
10-404491-00
10-433652-00
10-433674-00
10-438446-00
10-438732-00
10-439392-00
10-440841-00
10-449752-00
10-451035-00
10-453615-00
10-454051-00
10-462600-00
10-462749-00
17-145168-00
515-094464-001
515-094464-002
524-327898-001
524-327903-001
524-344228-035
524-344228-036
524-344228-037
714-157315-005
714-360155-002
715-144766-002
715-253892-001
715-333899-001
715-337095-160
718-207317-001
718-207317-002
718-293653-001
796-333809-001
839-004572-003
839-006275-002
839-016784-005
839-017586-056
839-026927-001
839-029699-002
839-029721-002
839-033524-001
839-033524-002
839-037494-001
839-038208-001
839-039628-001
839-039628-002
839-039629-001
839-050650-010
839-050650-012
839-054297-212
839-054297-636
839-054297-675
839-056432-002
839-057594-206
839-072865-022
839-072866-022
839-072888-122
839-072889-122
839-076970-017
839-078338-002
839-080894-062
839-080894-064
839-084410-006
839-087162-002
839-087163-002
839-087480-011
839-100488-001
839-100488-002
839-103773-001
839-115116-003
839-116402-001
839-116402-002
839-117183-001
839-117184-001
839-117185-001
839-117186-001
839-117258-006
839-117258-007
839-128995-001
839-129835-003
839-144765-023
839-150277-004
839-150438-001
839-150439-001
839-150824-102
839-150824-103
839-150824-200
839-151551-002
839-151551-003
839-151551-004
839-151551-005
839-152182-006
839-155636-001
839-157049-016
839-158565-002
839-160846-001
839-161246-005
839-161593-082
839-161593-099
839-161593-180
839-162438-001
839-162438-015
839-162438-016
839-163723-001
839-163723-102
839-163725-101
839-164630-001
839-164630-002
839-166314-002
839-166484-003
839-166484-005
839-166567-001
839-166569-001
839-166784-003
839-166802-002
839-167321-001
839-167697-003
839-167964-001
839-169273-001
839-169281-001
839-170620-007
839-172323-001
839-172326-001
839-172349-001
839-173615-001
839-173615-003
839-173615-004
839-173615-005
839-173615-006
839-174692-003
839-174812-001
839-175475-001
839-175862-001
839-176148-001
839-176150-001
839-176154-001
839-176155-001
839-176232-002
839-177616-001
839-177633-001
839-177633-004
839-178312-001
839-179382-004
839-179807-001
839-181110-005
839-182815-001
839-183946-001
839-184282-001
839-185831-001
839-186428-015
839-186428-016
839-186428-017
839-186707-001
839-187802-010
839-188389-001
839-190456-007
839-190456-009
839-192938-001
839-195294-001
839-196163-003
839-197078-001
839-197078-010
839-197334-001
839-197477-001
839-197878-002
839-197878-004
839-197878-005
839-197878-008
839-197878-201
839-198666-004
839-199426-003
839-199810-003
839-199811-002
839-200744-001
839-200778-001
839-200790-003
839-200882-001
839-200941-001
839-200942-001
839-200943-001
839-201106-002
839-201346-010
839-201346-012
839-201347-002
839-201347-012
839-202006-002
839-203225-001
839-203225-002
839-203225-003
839-203225-004
839-203225-005
839-203225-006
839-203666-002
839-203816-001
839-203816-002
839-203816-003
839-203816-004
839-203817-001
839-203818-001
839-203818-002
839-203818-003
839-204125-001
839-204125-002
839-205071-001
839-205178-001
839-205294-001
839-206148-002
839-207141-001
839-207300-002
839-208745-001
839-209648-002
839-209731-001
839-211602-003
839-212647-003
839-213679-001
839-213703-001
839-213914-001
839-216497-011
839-216497-014
839-216497-015
839-216497-017
839-216497-018
839-223871-002
839-224543-022
839-224543-023
839-224543-030
839-224543-035
839-224899-101
839-224938-002
839-225084-002
839-227595-001
839-227596-001
839-227886-002
839-227887-001
839-228532-002
839-229013-001
839-229890-001
839-229890-002
839-230150-002
839-230153-001
839-230349-002
839-230387-001
839-231103-025
839-232238-006
839-232238-034
839-232238-051
839-232238-081
839-232238-091
839-232443-001
839-233534-001
839-233670-002
839-233940-001
839-233940-002
839-234926-001
839-234927-001
839-234928-638
839-234928-837
839-235917-200
839-236158-001
839-236248-002
839-237237-001
839-237336-002
839-237336-004
839-242763-001
839-245126-002
839-249023-700
839-249959-006
839-251515-001
839-251618-003
839-251618-004
839-252622-002
839-252640-210
839-254430-302
839-254633-202
839-255755-115
839-256146-003
839-256943-003
839-257399-001
839-257439-001
839-257655-001
839-257735-002
839-258143-001
839-258421-001
839-258707-201
839-261083-001
839-261084-001
839-261142-001
839-262025-001
839-262082-001
839-262398-001
839-262413-017
839-262416-001
839-262418-001
839-262560-011
839-264393-001
839-264664-001
839-264673-001
839-264690-001
839-264699-001
839-266281-001
839-266517-001
839-270263-002
839-270263-003
839-270263-102
839-270380-001
839-270450-914
839-270527-001
839-271189-001
839-271657-001
839-271657-002
839-271658-001
839-271660-001
839-271661-001
839-271677-201
839-271677-203
839-271677-204
839-271677-205
839-272405-008
839-274181-003
839-274181-212
839-274396-001
839-275547-701
839-275633-001
839-276495-001
839-276853-001
839-276861-001
839-276869-002
839-277140-102
839-278317-001
839-278591-002
839-278592-002
839-283878-003
839-285194-702
839-285643-002
839-285733-003
839-285737-002
839-285802-001
839-287955-021
839-287955-023
839-288471-012
839-288471-013
839-288471-015
839-288471-016
839-288471-702
839-290814-001
839-292695-002
839-293138-006
839-293138-007
839-293138-008
839-293840-001
839-293948-001
839-295407-001
839-295544-002
839-295549-002
839-295808-001
839-296797-003
839-296797-004
839-296931-002
839-297844-001
839-299301-001
839-299345-002
839-301032-001
839-301499-001
839-301650-001
839-302964-002
839-302967-002
839-303411-002
839-303569-002
839-306725-001
839-306778-001
839-306913-001
839-309745-001
839-310294-020
839-311279-001
839-311280-001
839-311844-001
839-312063-001
839-313131-001
839-315079-010
839-315079-012
839-315287-001
839-315640-020
839-315641-020
839-315642-020
839-316680-002
839-316801-002
839-316834-002
839-316835-002
839-316836-002
839-317830-033
839-317830-036
839-317830-576
839-317830-879
839-317830-890
839-317830-893
839-317830-952
839-317830-973
839-317830-978
839-317966-003
839-317967-003
839-319115-003
839-319115-010
839-319115-011
839-319461-002
839-319649-002
839-321132-001
839-326105-002
839-326540-001
839-326540-005
839-326540-006
839-326540-007
839-327486-002
839-327690-002
839-330558-001
839-331154-614
839-331651-001
839-331706-001
839-331708-001
839-331712-001
839-331713-001
839-332469-002
839-332880-001
839-333212-003
839-333513-002
839-333626-001
839-334130-001
839-335462-120
839-335490-002
839-335490-009
839-335490-011
839-335490-018
839-335836-011
839-335836-012
839-335836-013
839-336389-203
839-336389-602
839-337110-001
839-337756-001
839-338171-001
839-338177-001
839-339554-025
839-339939-002
839-340513-001
839-345274-001
839-345277-001
839-345278-001
839-345279-001
839-345282-001
839-360161-003
839-370553-002
839-470847-103
839-470847-203
839-470868-101
839-470876-014
839-470876-024
839-800970-401
839-801255-020
839-801796-001
839-802506-229
839-802753-017
839-802783-004
839-802785-002
839-803173-020
839-810334-001
839-A00617-001
839-A00622-001
839-A02055-016
839-A02055-036
839-A02067-016
839-A02069-016
839-A02384-001
839-A04676-001
839-A04729-001
839-A06314-300
839-A07274-001
839-A07893-002
839-A08127-001
839-A09684-012
839-A09684-013
839-A11153-003
839-A11451-001
839-A11804-005
839-A12452-011
839-A12809-001
839-A12956-001
839-A13282-001
839-A13905-001
839-A14038-001
839-A14427-010
839-A20409-019
839-A20409-052
839-A20409-059
839-A20409-094
839-A20409-194
839-A20409-198
839-A20409-245
839-A20409-307
839-A20409-308
839-A20409-362
839-A20409-703
839-A21082-001
839-A21084-001
839-A21211-001
839-A21657-010
839-A21657-011
839-A21659-012
839-A21855-001
839-A22404-001
839-A24405-001
839-A24410-001
839-A24451-001
839-A24686-002
839-A26554-001
839-A27585-001
839-A28990-001
839-A29936-001
839-A29937-001
839-A29938-001
839-A29967-003
839-A29967-011
839-A30834-001
839-A31376-001
839-A32067-002
839-A32071-004
839-A33166-001
839-A33167-001
839-A33172-001
839-A33176-001
839-A33556-001
839-A33558-001
839-A33740-002
839-A33982-002
839-A34410-234
839-A34450-011
839-A36237-001
839-A37722-001
839-A37821-001
839-A37822-001
839-A37827-001
839-A38767-001
839-A39663-002
839-A41194-013
839-A41194-014
839-A41426-001
839-A41781-002
839-A41937-001
839-A41949-001
839-A41949-002
839-A42151-001
839-A42292-001
839-A42297-001
839-A42305-001
839-A42454-001
839-A42455-001
839-A42457-001
839-A42483-001
839-A42493-001
839-A42505-001
839-A42524-001
839-A42526-001
839-A47170-001
839-A47172-001
839-A47215-001
839-A47256-001
839-A47443-002
839-A47444-002
839-A50689-001
839-A51800-001
839-A58913-305
839-A58914-305
839-A64372-018
839-A69004-001
839-A70054-002
853-113120-001
853-142645-002
853-231274-001
853-231274-002
853-286997-700
853-288953-003
853-291271-001
853-326581-002
853-347282-001
853-A03416-022
853-A03419-011
853-A12606-001
853-A35998-031
857-032441-102
857-A27504-001
A34-078-01
839-262560-005 | NC |  |  | Group 1 |  |  | Approved | 4502364348 | PO/Demand Issues | PRD-0495775 | 2958465 |  | Per Lam, move forward, and decline cancel on dashboard |  |  |  | 1
839-272303-001 | NC | Y |  | Group 1 |  | 4700636549 | TBD |  | Material Review |  | TBD | [5 empty] | 24
839-272306-001 | NC | Y |  | Group 1 |  | 4700636549 | TBD |  | Material Review |  | TBD | [5 empty] | 24
839-272464-001 | NC | Y | N | Group 2 | 07 | 4700631437 | TBD | 4700631439 | Material In Transit | PRD-0494697 PRD-0494698 | 2022-02-04 |  | 1-24dg 08.0-3960 PO-174661 due 1-28 AMERIFLEX, |  | X |  | 17
839-273122-005 | NC | Y | N | Group 2 |  | 4700634099 | TBD | 4700634160 | Eng Queue | PRD-0498527 PRD-0498528 PRD-0498529 | TBD |  | PRD PRD-0498528 not attached to sales line PRD-0498527 Scheduled PRD-0498529 Scheduled |  |  |  | 7
839-273122-006 | NC | Y | N | Group 2 |  | 4700634099 | TBD | 4700634160 | Started-Wip | PRD-0498531 PRD-0498533 | 2022-01-27 | [5 empty] | 6
839-273122-008 | NC | Y | N | Group 2 |  | 4700634099 | TBD | 4700634160 | Material In Transit | PRD-0498534 PRD-0498535 | 2022-02-18 |  | 1-26dg GDP01393 PO-172174 due 2-11 windustrl |  |  |  | 25
839-273153-001 | NC | Y | N | Group 2 | 03 | 4700631437 | TBD | 4700631439 | Material In Transit | PRD-0494713 | 2022-02-17 |  | 1-18dg PB-8 PO-174890 due 2-11 swalok |  |  |  | 17
839-273153-002 | NC | Y | N | Group 2 |  | 4700631437 | TBD | 4700631439 | Material Review | PRD-0494721 PRD-0494722 | TBD |  | PR submitted for BOM wrong 01/03/21 |  |  |  | 17
839-273816-001 | C4 | Y | N | Group 2 | 03 | 4700633237 | TBD | 4700633453 | Material In Transit | PRD-0494735 PRD-0494736 | 2022-03-30 |  | 1-24dg 08.1-1993 PO-174661 3-21 AMERIFLEX, 60 day LT |  |  | X | 22
839-274008-001 | C4 | Y |  | Group 2 |  | 4700633748 | TBD | 4700633749 | Material In Transit | PRD-0496824 | 2022-05-10 |  | 1-24dg 11.02-1420 PO-175338 due 5-2 Amerflx |  |  |  | 72
839-274019-001 | C4 | Y |  | Group 2 |  | 4700633748 | TBD | 4700633749 | Material Review | PRD-0497404 PRD-0497405 PRD-0497431 | TBD | [5 empty] | 96
839-274022-001 | C4 | Y |  | Group 2 |  | 4700633748 | TBD | 4700633749 | Started-Wip | PRD-0497445 PRD-0497446 | 2022-01-31 |  | in estimated PRD-0497446 |  |  |  | 182
839-274027-001 | C4 | Y | N | Group 2 | 03 | 4700633232 | 2022-01-11 | 4700633452 | Complete | PRD-0494751 PRD-0494717 | 2022-01-14 | 1-7dg PRD-0494717 | 1-7dg PRD-0494751 GDP00540 PO-172597 due 1-26 swaglok |  |  | X | 22
839-274148-001 | C4 | Y | N | Group 2 |  | 4502379205 | TBD | 4700633452 | At Fair | PRD-0495316 PRD-0495317 | 2022-01-21 | 1-14dg | FAI- Update Jan28 New 4500 PO recieved |  |  | X | 22
839-274183-001 | C4 | Y |  | Group 2 |  |  | TBD |  | Eng Queue |  | TBD |  | PRD not attached to sales line |  |  |  | 47
839-274392-001 | C4 | Y |  | Group 2 |  | 4700633749 | TBD | 4700633749 | Removed from List |  | TBD | VALIDATED, REMOVED | No bid |  |  |  | 0
839-276623-001 | NC | Y | N | Group 2 |  | 4700633232 | TBD | 4700633452 | Material In Transit | PRD-0495322 PRD-0495323 | 2022-03-22 |  | 1-24dg 08.0-6003 PO-175001 due 3-15 amerflx 1-24dg PLT4S-C0 PO-175536 due 1-25 Allied |  |  | X | 18
839-276623-002 | NC | Y | N | Group 2 |  | 4700633232 | TBD | 4700633452 | Material In Transit | PRD-0495347 PRD-0495348 | 2022-03-22 |  | 1-17dg 08.0-6003 PO-175001 due 3-15 amerflx 1-17dg PLT4S-C0 need PO |  |  | X | 17
839-276623-003 | NC | Y | N | Group 2 |  | 4700633236 | TBD |  | Material Review | PRD-0496622 | TBD |  | In LSR approval cycle, Buyer is Donna Metzler |  |  |  | 0
839-277137-001 | C4 | Y |  | Group 1 |  | 4700636549 | TBD |  | Material Review |  | TBD | [5 empty] | 10
839-277137-003 | NC |  |  | Group 1 |  |  | TBD | 4502364349 | PO/Demand Issues | PRD-0496070 | 2958465 |  | Per Lam, move forward, and decline cancel on dashboard |  |  |  | 6
839-285733-005 | NC |  |  | Group 2 |  | 4502354159 | TBD |  | Material Review |  | TBD | [5 empty] | 16
839-288018-001 | NC |  |  | Group 1 |  |  | Approved | 4502364356 | PO/Demand Issues | PRD-0496087 | 2958465 |  | Per Lam, move forward, and decline cancel on dashboard |  |  |  | 2
839-290061-002 | NC | Y |  | Group 2 |  | 4700633748 | TBD | 4700633749 | Material Review |  | TBD |  | RFQ submitted 1/17 - PO still reflects pennyPO . 1/19 - Eng request Step File |  |  |  | 23
839-290061-003 | NC | Y |  | Group 2 |  | 4700634099 | TBD | 4700634160 | Material Review |  | TBD |  | 1/19 - Eng request Step File |  |  |  | 5
839-290061-004 | NC | Y | N | Group 2 | 03 | 4700634099 | 2022-01-11 | 4700634160 | Complete | PRD-0495320 PRD-0495321 | 2022-01-14 | 1-7dg 1-7dg |  |  |  | X | 25
839-290061-008 | NC | Y | N | Group 2 |  | 4502379170 | TBD | 4700634160 | At Fair | PRD-0495401 PRD-0495402 | 2022-01-20 | 1-8dg both PRD's | FAI - Update Jan29 - New 4500 PO recieved: |  |  | X | 5
839-298117-001 | NC | Y | N | Group 2 | 03 | 4700630852 | 2022-01-13 | 4502349969 | Complete | PRD-0492520 PRD-0492521 | 1-198 | 1-8dg both PRD's |  |  | X | X | 7
839-298118-001 | NC | Y | N | Group 2 |  | 4700635032 | Approved | 4502365647 | Complete | PRD-0496633 | 2022-01-28 | [5 empty] | 7
839-308304-001 | NC | Y | N | Group 2 | 03 | 4700630853 | 2022-01-13 | 4502349972 | Complete | PRD-0492479 PRD-0492490 | 2022-01-18 | 1-8dg both PRD's |  |  |  | X | 5
839-309157-001 | NC | Y |  | Group 1 |  | 4700636549 | TBD |  | Material Review |  | TBD | [5 empty] | 8
839-317073-001 | NC | Y | N | Group 2 |  | 4700630854 | Approved | 4502349973 | Complete | PRD-0492268 PRD-0494347 | 2022-01-19 | 1-8dg both PRD's |  |  |  |  | 8
839-320045-002 | NC |  |  | Group 1 |  | 4502364365 | TBD | 4502364365 | PO/Demand Issues |  | 2958465 |  | Per Lam, move forward, and decline cancel on dashboard |  |  |  | 15
839-323472-002 | NC | Y | N | Group 2 | 03 | 4700631438 | TBD | 4700631440 | Material Gated | PRD-0495040 | TBD |  | 1-25dg 6LV-2MW-9 PO-175763 need confrmd swaglok |  |  | X | 4
839-323472-003 | NC | Y | N | Group 2 |  | 4700631438 | TBD | 4700631440 | Material Review | PRD-0494980 | TBD |  | 1-24dg no BOM |  |  | X | 4
839-323472-005 | NC | Y | N | Group 2 | 03 | 4700633217 | TBD | 4700633219 | Material Gated | PRD-0495403 PRD-0495404 | TBD |  | 1-25dg 6LV-2MW-9 PO-175763 need confrmd swaglok |  |  | X | 4
839-325328-002 | NC |  |  | Group 1 |  |  |  |  | Removed from List |  | TBD | VALIDATED, REMOVED | No PO on dashboard, PO week of 1/17 |  |  |  | 0
839-330146-003 | CV |  |  | Group 2 |  | 4700625847 | TBD |  | Material Review |  | TBD |  | 1/18 Eng submitted PR-095738, ASA issued, releasing today |  |  |  | 76
839-333435-006 | NC | Y | N | Group 2 |  | 4502379205 | TBD | 4700633452 | At Fair | PRD-0494693 PRD-0494695 | 2022-01-19 | 1-8dg both PRD's | FAI-Update Jan28 New 4500 PO recieved |  |  | X | 8
839-333435-007 | NC | Y | N | Group 2 |  | 4502379205 | TBD | 4700633452 | At Fair | PRD-0495405 PRD-0495406 | 2022-01-20 | 1-8dg PRD-0495406 | FAI-Update Jan28 New 4500 PO recieved |  |  | X | 8
839-333435-008 | NC | Y | N | Group 2 |  | 4502379205 | TBD | 4700633452 | At Fair | PRD-0495407 PRD-0495408 | 2022-01-20 | 1-8dg PRD-0495408 | FAI- Update Jan 28 New 4500 PO recieved |  |  | X | 8
839-333435-009 | NC | Y | N | Group 2 | 03 | 4700633236 | Approved | 4700633453 | Complete | PRD-0494727 | 2022-01-18 | 1-7dg |  |  |  | X | 8
839-333435-010 | NC | Y | N | Group 2 | 03 | 4700633236 | Approved | 4700633453 | Complete | PRD-0494706 PRD-0494707 | 2022-01-14 | 1-7dg 1-7dg |  |  |  | X | 8
839-333435-011 | NC | Y | N | Group 2 | 03 | 4700633236 | Approved | 4700633453 | Complete | PRD-0494696 PRD-0494699 | 2022-01-14 | 1-7dg 1-7dg |  |  |  | X | 8
839-333540-001 | NC |  |  | Group 1 |  | 4502356597 | Submitted | 4502356597 | Complete | PRD-0495065 | 2022-01-24 | [5 empty] | 20
839-333541-001 | NC |  |  | Group 1 |  |  | Approved | 4502356598 | PO/Demand Issues | PRD-0494101 | 2022-06-27 |  | Doesn't seem to be needed until June. Resolved? |  |  |  | 18
839-334033-001 | NC |  |  | Group 2 |  | 4700625847 | TBD |  | Started-Wip | PRD-0494103 | 2022-01-21 | [5 empty] | 48
839-338158-001 | C4 |  |  | Group 2 |  | 4700625847 | TBD |  | Complete | PRD-0494095 | 2022-01-20 |  | shipped; no FAI submitted in portal |  |  |  | 32
839-800970-105 | NC | Y |  | Group 1 |  |  |  |  | Removed from List |  | TBD | VALIDATED, REMOVED | No PO on dashboard, PO week of 1/17 |  |  |  | 0
839-802321-001 | CV | Y |  | Group 2 |  | 4700633748 | TBD | 4700633749 | Started-Wip | PRD-0494677 PRD-0494686 | 2022-01-20 | 1-13dg PRD-0494677 | 1-13dg PRD-0494686 GDP00524 need PO swaglok |  |  |  | 64
839-802495-122 | NC |  |  | Group 1 |  | 4502364367 | TBD | 4502364367 | PO/Demand Issues |  | 2958465 |  | Per Lam, move forward, and decline cancel on dashboard |  |  |  | 9
839-802568-012 | NC |  |  | Group 1 |  |  | Approved | 4502214674 | Complete | PRD-0481333 | 2022-01-12 | [5 empty] | 31
839-803173-010 | CV | Y | N | Group 2 | 03 | 4700633220 | TBD | 4700633221 | Material In Transit | PRD-0494734 | 2022-02-14 |  | 1-20dg 6LVV-4-VCR-3-02205 PO-174859 PO-174859 due 3-28 swagok |  |  | X | 1525
839-A05141-001 | NC |  |  | Group 1 |  |  | Approved | 4502364375 | Material In Transit | PRD-0496073 | 2022-03-09 |  | 1-25dg 790-250991-031 PO-175327 due 3-2 TALON |  |  |  | 5
839-A10966-001 | NC |  |  | Group 1 |  |  | Approved | 4502364727 | PO/Demand Issues | PRD-0496115 | 2958465 |  | Cancel message, Talus? |  |  |  | 1
839-A12224-001 | NC |  |  | Group 1 |  |  | Approved | 4502364734 | Started-Wip | PRD-0496123 | 2022-01-19 | [5 empty] | 2
839-A12431-002 | NC |  |  | Group 1 |  |  | Approved | 4502364735 | Complete | PRD-0496124 | 2022-01-21 | 1-14dg |  |  |  |  | 3
839-A23650-001 | NC |  |  | Group 1 |  |  | Approved | 4502364737 | PO/Demand Issues | PRD-0496126 | 2958465 |  | Cancel message, Talus? Also has shortages from: Scheduled. 6LV-4MW-9-03442P 8.00 (PO-172597 02/09/2022 30.00 SWAGELOK N ) ¦ 6LV-4MW-9P 6.00 (Plo. MPO-6697158 02/08/2022 3536.50 8974 ) ¦ 790-250991-031 2.00 (NoC. PO-174297 03/03/2022 8.00 TALON INNO ) ¦ SS-4-VCR-4 2.00 (Plo. MPO-6697633 02/08/2022 440.30 8974 ) ¦ |  |  |  | 1
839-A24545-001 | NC |  |  | Group 1 |  |  | Approved | 4502364740 | Material Gated | PRD-0496128 |  |  | 1-25dg 790-250991-031 PO-174297 need confrmd TALON (need |  |  |  | 3
839-A25107-001 | NC | Y |  | Group 1 |  | 4700636549 | TBD |  | Material Review |  | TBD | [5 empty] | 9
839-A25903-001 | NC | Y |  | Group 1 |  |  | Approved | 4502240159 | Complete | PRD-0462599 | 2022-01-20 | 2022-01-12 |  |  |  |  | 0
839-A25903-002 | NC | Y |  | Group 1 |  |  | Approved | 4502333791 | Complete | PRD-0487272 | 2022-01-19 | 2022-01-12 |  |  |  |  | 1
839-A25903-003 | NC | Y |  | Group 1 |  | 4502333791 | TBD | 4502333791 | Complete | PRD-0487273 | 2022-01-24 | [5 empty] | 1
839-A25903-004 | NC | Y |  | Group 1 |  |  | Approved | 4502240159 | Complete | PRD-0462601 | 2022-01-20 | 2022-01-12 |  |  |  |  | 0
839-A27829-001 | NC |  |  | Group 1 |  |  | Approved | 4502364741 | Material In Transit | PRD-0496129 | 2022-01-28 | [5 empty] | 7
839-A42757-002 | CV |  |  | Group 1 |  | 4700636549 | TBD |  | PO/Demand Issues |  | TBD |  | Penny PO - item has been quoted and submitted to Lam |  |  |  | 2
853-083795-045 | C4 | Y | N | Group 2 |  |  | TBD |  | Removed from List |  | TBD | VALIDATED, REMOVED | No bid, MDC cannot disassemble/reassemble valves and plastic suppliers no bid MDCs RFQ |  |  |  | 298
853-193770-004 | NC |  |  | Group 2 |  | 4700632959 | TBD |  | Material In Transit | PRD-0495266 | 2022-02-14 |  | 1-13dg sub assy 839-346961-002 PRD-0495267 --1-13dg 839-346961-002-1 PO-174811 due 1-31 AR Machining --1-13dg 839-346961-002-2 PO-174811 due 1-31 AR Machining --1-13dg 839-346961-002-3 PO-174811 due 1-31 AR Machining |  |  |  | 87
853-257240-001 | NC | Y | N | Group 2 |  | 4700633237 | TBD | 4700633453 | Removed from List |  | TBD | VALIDATED, REMOVED | NO BID - cannot build to print |  |  |  | 25
853-304133-002 | NC | Y |  | Group 1 |  | 4700636549 | TBD |  | Material Review |  | TBD | [5 empty] | 74
853-A05403-004 | NC | Y | N | Group 2 |  | 4700633237 | TBD | 4700633453 | Eng Queue | PRD-0498349 PRD-0498351 PRD-0498352 | TBD |  | Pricing updated in PO |  |  |  | 20
857-223231-001 | NC | Y | N | Group 2 |  | 4700631438 | TBD | 4700631440 | Eng Queue | PRD-0498958 PRD-0498959 | TBD |  | Pricing updated in PO |  |  |  | 9

## Materials Status
DATE ADDED | PRD | PART NO | PART NUMBER | PO NUMBER | DUE DATE | SUPPLIER | COMMENT | LAM Available | ALT1 Supplier | ALT1 PN | Date | ALT2 Supplier | ALT2 PN | Date
2022-01-10 | PRD-0494734 | 839-803173-010 | 6LVV-4-VCR-3-02205 | PO-174859 | 5 qty, due 3/29/2022 ; x900 pending response fr Supplier | Swagelok | need min x5 asap for FA // 1-12 AR 19 week lead time for line 2 but Swagelok looking for this part at a sister Swagelok. 5 qty due 03/29/22 - 900qty due 12/07/2023... Partials OK, need shceduled releases/ looking for potential sub. -Checking broker stock, Swagelok Malaysia has 197 - Contacted Drew 1-20 Exp fee applied (getting x900 fr Swagelok Malaysia). 1-21 Asked for ship date. 1-25 & 1-26 asked for tracking; advised on 1-26 going through customs now should have tracking Friday. 1-28 Asked Swagelok for status of incoming shipment.
2022-01-10 | PRD-0494734 | 839-803173-010 | 6LVV-4-VCR-3S-4TB2 | PO-174998 | 2023-05-25 | Swagelok | 6LVV-4-VCR-3S-4TB2(P) CONS PART READILY AVAILBLE, BETTER PART AR 1-11 target date is 05/23 due to this being a factory made item - Purchase x5 from LAM - PO sent to LAM - IN stock - Need PR for P version. 1-28 AR Fllowed up to see if any improvement on Swage PO. Tried to cancel Swagelok PO, but NCNR. | 5 | Fujikin | UJR-6.35MS-AW-S-316LP |  | Parker | 4-4V1M-SSV .035-PR
2022-01-10 | PRD-0495284 | 839-204868-003 | 839-204868-003-A01 | PO-174915 | 2022-01-31 | B2 maching | B2 Machining are doing everything they can to pull this date in. Right now, we are on track for our 1/31/22 delivery date given. We will let you know if anything changes. updated 1/21/22
2022-01-10 | PRD-0495291 | 839-101870-902 | 839-101870-902-2 | PO-174811/PO-175003 | 1/31/2022 - 02/16/22 | A.R. MACHINING, INC | po-174811 7QTY DUE 01/31 . Po-175003 QTY 90 due 02/16 - Request for Expedite!!! - Sent 1/18 & 1/21 - AR Machining - HAVE ACCELERATED ALL THE PARTS LISTED BELOW. WE WILL BE ABLE TO GIVE YOU A MORE FIRM DELIVERY DATE EARLY NEXT WEEK. THE PRODUCTION TEAM WILL BE MEETING AGAIN ON MONDAY TO REVIEW ALL THESE PARTS REGARDING STATUS. IF THERE ARE ANY THAT MIGHT NEED TO GO TO OUTSIDE SERVICES ( EP OR CLEAN ) THEY WILL PROBABLY REQUEST EXP FEES. updated 1/21/22
2022-01-10 | PRD-0495394 | 10-413657-00 | 4.00X.083 304 | po-175578 | 2022-01-31 | Win Supply | sent po-174306 due 07/08 24 week l/t Winsupply PO-175578, They have 500 Ft. scheduled to ship from the factory the first week in February. ETA 2/9 - delivery their truck
2022-01-10 | PRD-0495394 | 10-413657-00 | 10-413657-00-2 | PO-174895 | 2022-02-23 | A.R. MACHINING, | qty 77 partials ok - Request for Expedite!!! - Sent 1/18 & 1/21 - AR Machining - HAVE ACCELERATED ALL THE PARTS LISTED BELOW. WE WILL BE ABLE TO GIVE YOU A MORE FIRM DELIVERY DATE EARLY NEXT WEEK. THE PRODUCTION TEAM WILL BE MEETING AGAIN ON MONDAY TO REVIEW ALL THESE PARTS REGARDING STATUS. IF THERE ARE ANY THAT MIGHT NEED TO GO TO OUTSIDE SERVICES ( EP OR CLEAN ) THEY WILL PROBABLY REQUEST EXP FEES. updated 1/21/22
2022-01-10 | PRD-0495394 | 10-413657-00 | 11.00-1600 | PO-175001 | 2022-02-16 | AMERIFLEX, | Expedite - 4 weeks
2022-01-10 | PRD-0494720 | 839-239359-003 | 839-239359-003-COIL | PO-174900 | 2022-01-27 | CAPITAL BENDING | Current date 1/27, attempting expedite with fees - Capital Bending can not offer an expo for this one due to tubing lead time - Per your conversation with Keith yesterday, T4A-QS-.13X4-028B0 may ship from the factory at the end of January. This tubing was originally scheduled to ship early January, but has been pushed out weekly so we can’t be sure of the ship date until the factory provides tracking info. Transit to Austin is usually 5-7 Working Days. Adam at Capital Bending will check periodically and keep you posted.
2022-01-10 | PRD-0494721 | 839-273153-002 | PB-8-RD | PO-175474 | 2022-01-28 | LAM | 1-13 AR on back order, but was able to pull-in to 2-23. Checking other Swagelok Disty - Order from LAM ASAP. 1-27 Followed up to confirm Feb dock & if Swage was able to improve. | 26
2022-01-10 | PRD-0494713 | 839-273153-001 | PB-8 | PO-175474 | 2022-01-28 | LAM | qty 95 / qty 5 1-13 PO-174890 pulled into 2-11. PO-174285 due 2-14 (Swagelok unable to pull-in). Parts on back order. Dates are the soonest we can have them available. Order from LAM ASAP. 1-18 LAM PO-175474 was issued. | 35
2022-01-10 | PRD-0494735 | 839-273816-001 | 08.1-1993 | PO-174661 | 2022-01-19 | AMERIFLEX, | Alternate Part indentified (Compuvac) - send to MDC Engineering for review. Will order after review Part ordered from Compuvac
2022-01-10 | PRD-0495323 | 839-276623-001 | 08.0-6003 | PO-175001 | 2022-03-21 | AMERIFLEX, | Ameriflex Unable to expedite. Specs sent to Compuvac, returned with cross reference and quote. 10-12 day lead time. Requested part set-up for immediate purchase in advance of approval. Part ordered from Compuvac 1/24/2022
2022-01-10 | PRD-0492711 | 839-229542-002 | 839-229542-002-1,4,5 | PO-174615 | 2022-01-27 | A&T | expedite with fees requested
2022-01-10 | PRD-0495279 | 10-149847-00 | GDP00024 | PO-174255 | 2022-02-01 | windustrl | delivery ASAP for ICHOR project // PO placed 12-21 10 day LT in AX/ sub - Request for Expedite!!! - Sent 1/18 & 1/21 -
2022-01-18 | PRD-0495266 | 853-193770-004 |  | PO-174811 | 2022-01-31 | AR Machining | 1-13dg sub assy 839-346961-002 PRD-0495267 --1-13dg 839-346961-002-1 PO-174811 due 1-31 AR Machining --1-13dg 839-346961-002-2 PO-174811 due 1-31 AR Machining --1-13dg 839-346961-002-3 PO-174811 due 1-31 AR Machining - Request for Expedite!!! - Sent 1/18 & 1/21 - AR Machining - HAVE ACCELERATED ALL THE PARTS LISTED BELOW. WE WILL BE ABLE TO GIVE YOU A MORE FIRM DELIVERY DATE EARLY NEXT WEEK. THE PRODUCTION TEAM WILL BE MEETING AGAIN ON MONDAY TO REVIEW ALL THESE PARTS REGARDING STATUS. IF THERE ARE ANY THAT MIGHT NEED TO GO TO OUTSIDE SERVICES ( EP OR CLEAN ) THEY WILL PROBABLY REQUEST EXP FEES. updated 1/21/22
2022-01-18 | PRD-0493004 | 10-374386-00 | 10-374386-00-01 | PO-174615 | 2022-01-27 | A&T | Due 1/27
2022-01-18 |  | 10-434785-00 | 2.00X.065 304L | PO-175578 | 2022-02-09 | Winsupply | Dale to advise/ AUSTIN has 200' available - PO 175578 - Winsupply of Silicon Valley - PN 2.00X.065 304L -500 Ft. scheduled to ship from the factory the first week in February.
2022-01-24 |  | 839-A05141-001 | 790-250991-031 | PO-175327 | need confrmd | TALON | Resolved through UCT
2022-01-25 |  | 10-417717-00 | 10-417717-00-02 | need PO |  | PROTRACK PRECISION
2022-01-26 | PRD-0497999 | 839-084412-799 | 785-038650-004 | need PO |  | SINE-TIFIC SOLUTIONS, INC.
2022-01-26 | PRD-0495288 | 10-255648-00 | GDP00524 | need PO
2022-01-27 | PRD-0497403 | 839-204868-001 | 839-204868-001-1 | PO-175434 | 2022-03-16 | A&T
2022-01-27 | PRD-0498000 | 839-084412-799 | 220-36747-000 | PO-176028 | 2022-03-02 | HYTRON | need delivery by 2-21
2022-01-28 |  | 839-274008-001 | 11.02-1420 | PO-175338 | 2022-05-02 | amerflx
2022-01-28 | PRD-0497446 | 839-274022-001 | 4.00X.083 304 | PO-174660 PO-175330 | need confrmd | RYAN HERCO FLOW SOLUTIONS | need delivery in Feb
2022-01-28 | PRD-0495394 | 10-413657-00 | 10-413657-00-2 | PO-174895 | 2022-02-11 | AR Machining | pull into as soon as possible
2022-01-28 | PRD-0496810 | 839-290061-002 | GDP01393 | PO-172174 | 2022-04-29 | windustrl | pull in confrm PO-175878 Feb delivery

## Action Items by Day
| LAM Owner | [8 empty] | LAM Owner
| MDC Owner | [8 empty] | MDC Owner
| Shared Action | [8 empty] | Shared Action
Date Opened | Owner | Action Needed | Update | Status | PR | Issue Summary | Status | ASA? | Action Needed | Owner
2022-01-25 | Ramya | Action the "CANCEL" message POs with actions for MDC | To cover in 1/25 afternoon session Ramya to release cancel message | Open | 095133 | Wall thickness discrepancy on MDC elbow 403501 (.035 vs .065) | In Work - Confirmed | No | Deviation approved, awaiting ASA | Lam
2022-01-25 | SQAD | Work through PRs on Playbook tab (bolded, 095133 and 094960) | Update in afternoon session 1/25: Sumanth on holiday, revisit 1/27. Esc to MI on 1/26 Response from Kala received, working through ASA steps on Lam side | Open | 094960 | Swagelok/Cajon part numbers | In Work - Confirmed | No | DST issued, release ASA to MDC | Lam
2022-01-25 | Dante/Kala | Find a solution for 6" radius elbow on PR-095664. MDC cannot do a 1pc bend, suggesting an elbow/tube/weld solution. | Looking up Duhig and others, DB reaching out to Kala on elbow details | Open | 095664 | 6" elbow substitution, MDC .109 wall radius elbow | Rejected | No | Kala working with Dante on details to review | Lam/MDC
2022-01-25 | Heidi | Add notes to Playbook tab on FAIR POs needing Lam conversion to 4500s | Notes added to Playbook tab | Done
2022-01-25 | Lance | Review "Remove from List" lines for validity | To be updated during 11am 1/26 mtg | Done | 096387 | Move CE parts to Austin site | Rejected | No | Matt working with Sumanth to submit proper CCC form | Lam
2022-01-25 | Ramya | Update 4700 POs needing conversion to 4500 POs | Albert working with buyers on list Ramya to process on 4500 POs (need to get MDC loaded as a supplier on Lam side) | Open | 096494 | Ameriflex substitution | Rejected, need Matt to help | No | Lam review and approval of Compuvac alternative, CCC notification | Lam
2022-01-26 | Lam | SCM saying to build in Austin (incl CE), SQAD saying no | NC/CE parts will need PR with Matt as contact. Non-CE, NC parts can move freely. Critical parts do not move. PR-096387 (and 85...) submitted, rejected. Matt working with Sumanth on CCC form | Open
2022-01-26 | Erick | Add Matt to SharePoint working file | Completed 1/26 after morning session | Done
2022-01-26 | Erick | Create email distribution address for material change topics | LamWarRoom@mdcprecision.com created | Done |  | 095664
2022-01-26 | Declan/Daryl | move 4/4 commit week lines into Q1 true commits | Daryl reviewing for updated by Fri 1/28 AM | Open
2022-01-26 | SQAD | Two final Ameriflex substitutions | Heidi working with Dante to submit PR using side by side data, ref Matt on PR PR-096494 submitted | Open
2022-01-27 | Milind/Anibal | Swagelok valve 719-230219-001 needed x1310 units for Q1 deliveries | Email Anibal and Milind part number and demand info (Done) Anibal to allocate/align dates with Swagleok Trevor checking on commit status and OO quantity with SNC | Open
2022-01-27 | Albert/Duri | Check Q1 demand on Lam side for all Group 1 and Group 2 parts (BI) | Albert/Duri to advise after review | Open
2022-01-27 | MDC Estimating | Open RFQ for MDC Austin vendor ID to quote transition parts | RFQs opened by Ameya MDC to quote parts on Austin ID portal | Open
2022-01-28 | Milind/Duri | PO's still being placed at $0.01, slowing the process | Milind to help escalate issue | Open
Review alternate options to SWG Ichor valve
Clarity to supply gate issues table, where Lam needs to provide support

## MDC Supply Commits
PartNumber | Second Supplier | Status | FAIR Completed Date | Past thru 1/23/2022 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | TTL PD-Mar28 | Issues/Notes
839-803173-010 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 120 | 130 | 130 | 130 | 130 | 130 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 905 | Swagelok arriving from MLY 2/7
839-078004-111 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863 | Swagelok dates TBD escalated
839-078004-112 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447 | Swagelok dates TBD escalated
839-274022-001 | MDC | Group 2 |  | 0 | 0 | 2 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226
839-204868-001 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 30 | 30 | 30 | 30 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 211 | Machined item being expedited (A&T)
839-084412-799 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 23 | 21 | 26 | 26 | 26 | 26 | 26 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | Partial commit from Hytron, working to improve more
839-204868-003 | MDC | Group 2 |  | 0 | 0 | 0 | 5 | 0 | 0 | 25 | 25 | 25 | 25 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | Aligned upon B2 machining arrival
839-274019-001 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 122 | HELP, Pricing is wrong, major loss on this part
839-802321-001 | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96
839-274008-001 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 93
10-413657-00 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74
10-418403-00 | MDC | Group 2 |  | 1 | 0 | 0 | 20 | 20 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | Aligned in Q1
839-173298-003 | MDC | Group 2 |  | 0 | 0 | 0 | 5 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
839-290061-002 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 30 | Aligned in Q1
839-239359-003 | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
839-274148-001 | MDC | Group 2 |  | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
839-179101-002 | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
10-422851-00 | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-422993-00 | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-422994-00 | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-423531-00 | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-434785-00 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
839-274027-001 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
839-285733-005 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
839-155217-002 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
10-374386-00 | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
10-296855-00 | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
853-A05403-004 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 18
839-276623-001 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 15
839-273816-001 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-276623-002 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 13
10-271948-00 | MDC | Group 2 |  | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-273153-001 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-273153-002 | MDC | Group 2 |  | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-153177-001 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 12
839-272464-001 | MDC | Group 2 |  | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
10-283365-00 | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
839-229542-002 | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
839-290061-004 | MDC | Group 2 |  | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
10-297758-00 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
839-330146-003 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
10-271203-00 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
839-298117-001 | MDC | Group 2 |  | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
839-298118-001 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
10-430901-00 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6
839-333435-008 | MDC | Group 2 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
857-223231-001 | MDC | Group 2 |  | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
19-047653-00 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-068732-006 | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-069366-808 | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-084411-001 | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-101870-902 | MDC | Group 2 |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-273122-008 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-334003-001 | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
10-143501-00 | MDC | Group 2 |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-333435-011 | MDC | Group 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-323472-005 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-266070-00 | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-323472-002 | MDC | Group 2 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-323472-003 | MDC | Group 2 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-149296-00 | MDC | Group 2 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-394919-00 | MDC | Group 2 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-445720-00 | MDC | Group 2 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-273122-005 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-290061-008 | MDC | Group 2 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-333435-006 | MDC | Group 2 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-333435-007 | MDC | Group 2 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-145276-07 | MDC | Group 2 |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
10-166680-00 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
839-245596-001 | MDC | Group 2 |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
839-333435-009 | MDC | Group 2 |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
10-149457-00 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
839-308304-001 | MDC | Group 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-317073-001 | MDC | Group 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-333435-010 | MDC | Group 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-151213-001 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-255648-00 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-143542-00 | MDC | Group 2 |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-146204-00 | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-149847-00 | MDC | Group 2 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-149893-00 | MDC | Group 2 |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-149926-00 | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-153142-00 | MDC | Group 2 |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-156309-00 | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-271377-00 | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-297760-00 | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-440436-00 | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-273122-006 | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-276623-003 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
839-290061-003 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-136163-02 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-143502-00 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-145276-06 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-150114-00 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-152277-00 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-152731-001 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-181110-002 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-198970-003 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-221767-001 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-229197-001 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-334033-001 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-338158-001 | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-132464-00 | MDC | Group 2 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
853-193770-004 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
02-424910-00 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-342125-00 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-410634-00 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15-431862-00 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16-421995-00 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16-421995-00 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-004572-155 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-078004-911 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-114189-010 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-179096-001 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-179097-001 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-274183-001 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-274183-001 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-274392-001 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
853-083795-045 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
853-257240-001 | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Part Count: | 88 |  |  |  |  | Part Count: | 25 | [5 empty] | Part Count: | 18
[6 empty] | Unit Count: | [5 empty] | Unit Count: | 2163 | [5 empty] | Unit Count: | 506

## Sheet2 (hidden)
RFQ
RFQ
PO/Demand Issues
Eng Queue
Material Review
Material Gated
Material In Transit
Started-Wip
At Fair
Complete
Removed from List

## Shortages Segmentation (hidden)
PART NUMBER | LAM PN | SUPPLIER | Supplier Type | Owners/Actions |  | Lam Stock?
91412 |  | grainger | Distributor
100760210 |  | MKS | OEM
08.0-3960 |  | AMERIFLEX, | OEM | LAM Stock Check / Ichor Stock Check
08.0-4000 |  | AMERIFLEX, | OEM | LAM Stock Check / Ichor Stock Check
08.0-6003 |  | AMERIFLEX, | OEM | LAM Stock Check / Ichor Stock Check
08.1-1993 |  | AMERIFLEX, | OEM | LAM Stock Check / Ichor Stock Check
101-MPC105
10-297758-00-3 |  | MOSS | Build-to-Print | MDC Supply Chain Escalation
10-413657-00-2 |  | A.R. MACHINING, | Build-to-Print | MDC Supply Chain Escalation
11.00-1600 |  | AMERIFLEX, | OEM | LAM Stock Check / Ichor Stock Check
11.02-2475 |  | AMERIFLEX, | OEM | LAM Stock Check / Ichor Stock Check
125X.028 316L |  | tube service | Distributor | MDC - Check All Distributors
142272 |  | Newark Element | Distributor | MDC - Check All Distributors
2WC-250 |  | Stainless Solutions | OEM | MDC Supply Chain Escalation / Check for Alternates | Use Nor-Cal G-2WC-250?
4.00X.083 304 |  | RYAN HERCO | Distributor | MDC Supply Chain Escalation
6LV-2-VCR-3S-2TB7P |  | Swagelok | OEM | MDC Supply Chain Escalation / Check for Alternates
6LV-8-VCR-3S-8TB3 |  | Swagelok | OEM | MDC Supply Chain Escalation / Check for Alternates
6LVV-4-VCR-3-02205 |  | Swagelok | OEM | MDC Supply Chain Escalation / Check for Alternates
6LVV-4-VCR-3S-4TB2 |  | Swagelok | OEM | MDC Supply Chain Escalation / Check for Alternates
785-322534-001 |  | Bradley Nameplate | Distributor | MDC - Check All Distributors
7W-250 |  | Stainless Solutions, | OEM | MDC Supply Chain Escalation | Use Nor-Cal G-7W-250?
839-101870-902-2 |  | A.R. MACHINING, INC | Build-to-Print | MDC Supply Chain Escalation
839-204868-003-A01 |  | B2 maching | Build-to-Print | MDC Supply Chain Escalation
839-229542-002-1,4,5 |  | A&T | Build-to-Print | MDC Supply Chain Escalation | 1/19/2022 A&T is not taking Expedites.But will try to pull in sooner.
839-239359-003-COIL |  | CAPITAL BENDING | Build-to-Print | MDC Supply Chain Escalation
GDP00024 |  | windustrl | Distributor | MDC - Check All Distributors
GDP00524 |  | SWAGELOK (CONSGT) | OEM | MDC Supply Chain Escalation / Check for Alternates
GDP00540 |  | Swagelok | OEM | MDC Supply Chain Escalation / Check for Alternates
GDP01330 |  | Swagelok | OEM | MDC Supply Chain Escalation / Check for Alternates
GDP01388 |  | windustrl | Distributor | MDC - Check All Distributors
GDP01544 |  | windustrl | Distributor | MDC - Check All Distributors
PB-8 |  | Swagelok | OEM | MDC Supply Chain Escalation / Check for Alternates
PB-8-RD |  | Swagelok | OEM | MDC Supply Chain Escalation / Check for Alternates
PLT1M-C10 |  | Allied Electronics | Distributor | MDC Supply Chain Escalation
SS-2-VCR-1 |  | Swagelok | OEM | MDC Supply Chain Escalation / Check for Alternates
SS-4-VCR-3-75LGP |  | Swagelok | OEM | MDC Supply Chain Escalation / Check for Alternates
SS-PB8-TA8 |  | Swagelok | OEM | MDC Supply Chain Escalation / Check for Alternates
T4A-QS-13X4-028B0 (GDP01544) |  | windustrl | Distributor | MDC - Check All Distributors

## lists (hidden)
RFQ
PO/Demand Issues
Eng Queue
Material Review
Material Gated
Started-Wip
At Fair
Complete
Removed from List

## MDC Supply Commits - updated
PartNumber | Type | Second Supplier | Status | FAIR Completed Date | Past thru 1/23/2022 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | TTL PD-Mar28 | Issues/Notes
839-803173-010 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 120 | 130 | 130 | 130 | 130 | 130 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 905 | Swagelok arriving from MLY 2/7
839-803173-010 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 120 | 130 | 130 | 130 | 130 | 130 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 905 | Swagelok arriving from MLY 2/7
839-078004-111 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863 | Swagelok dates TBD escalated
839-078004-111 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863 | Swagelok dates TBD escalated
839-078004-112 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447 | Swagelok dates TBD escalated
839-078004-112 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447 | Swagelok dates TBD escalated
839-274022-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 2 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226
839-274022-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 2 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226
839-204868-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 30 | 30 | 30 | 30 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 211 | Machined item being expedited (A&T)
839-204868-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 30 | 30 | 30 | 30 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 211 | Machined item being expedited (A&T)
839-084412-799 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 23 | 21 | 26 | 26 | 26 | 26 | 26 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | Partial commit from Hytron, working to improve more
839-084412-799 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 23 | 21 | 26 | 26 | 26 | 26 | 26 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | Partial commit from Hytron, working to improve more
839-204868-003 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 5 | 0 | 0 | 25 | 25 | 25 | 25 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | Aligned upon B2 machining arrival
839-204868-003 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 5 | 0 | 0 | 25 | 25 | 25 | 25 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | Aligned upon B2 machining arrival
839-274019-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 122 | HELP, Pricing is wrong, major loss on this part
839-274019-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 122 | HELP, Pricing is wrong, major loss on this part
839-802321-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96
839-802321-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96
839-274008-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 93
839-274008-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 93
10-413657-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74
10-413657-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74
10-418403-00 | Completed Shipments | MDC | Group 2 | 2022-01-10 | 1 | 0 | 0 | 20 | 20 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | Aligned in Q1
10-418403-00 | Supply Commits | MDC | Group 2 | 2022-01-10 | 1 | 0 | 0 | 20 | 20 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | Aligned in Q1
839-173298-003 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 5 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
839-173298-003 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 5 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
839-290061-002 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 30 | Aligned in Q1
839-290061-002 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 30 | Aligned in Q1
839-239359-003 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
839-239359-003 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
839-274148-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
839-274148-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
839-179101-002 | Completed Shipments | MDC | Group 2 | TBD | 0 | 5 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
839-179101-002 | Supply Commits | MDC | Group 2 | TBD | 0 | 5 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
10-422851-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-422851-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-422993-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-422993-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-422994-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-422994-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-423531-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-423531-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-434785-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-434785-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
839-274027-001 | Completed Shipments | MDC | Group 2 | 2022-01-11 | 1 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
839-274027-001 | Supply Commits | MDC | Group 2 | 2022-01-11 | 1 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
839-285733-005 | Completed Shipments | MDC | Group 2 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
839-285733-005 | Supply Commits | MDC | Group 2 | 00:00:00 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
839-155217-002 | Completed Shipments | MDC | Group 2 | 2022-01-10 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
839-155217-002 | Supply Commits | MDC | Group 2 | 2022-01-10 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
10-374386-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
10-374386-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
10-296855-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
10-296855-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
853-A05403-004 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 18
853-A05403-004 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 18
839-276623-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 15
839-276623-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 15
839-273816-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-273816-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-276623-002 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 13
839-276623-002 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 13
10-271948-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
10-271948-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-273153-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-273153-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-273153-002 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-273153-002 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-153177-001 | Completed Shipments | MDC | Group 2 | 2022-01-12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 12
839-153177-001 | Supply Commits | MDC | Group 2 | 2022-01-12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 12
839-272464-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
839-272464-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
10-283365-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
10-283365-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
839-229542-002 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
839-229542-002 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
839-290061-004 | Completed Shipments | MDC | Group 2 | 2022-01-11 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
839-290061-004 | Supply Commits | MDC | Group 2 | 2022-01-11 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
10-297758-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
10-297758-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
839-330146-003 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
839-330146-003 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
10-271203-00 | Completed Shipments | MDC | Group 2 | 2022-01-11 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
10-271203-00 | Supply Commits | MDC | Group 2 | 2022-01-11 | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
839-298117-001 | Completed Shipments | MDC | Group 2 | 2022-01-13 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
839-298117-001 | Supply Commits | MDC | Group 2 | 2022-01-13 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
839-298118-001 | Completed Shipments | MDC | Group 2 | Approved | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
839-298118-001 | Supply Commits | MDC | Group 2 | Approved | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
10-430901-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6
10-430901-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6
839-333435-008 | Completed Shipments | MDC | Group 2 | TBD | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
839-333435-008 | Supply Commits | MDC | Group 2 | TBD | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
857-223231-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
857-223231-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
19-047653-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
19-047653-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-068732-006 | Completed Shipments | MDC | Group 2 | TBD | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-068732-006 | Supply Commits | MDC | Group 2 | TBD | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-069366-808 | Completed Shipments | MDC | Group 2 | TBD | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-069366-808 | Supply Commits | MDC | Group 2 | TBD | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-084411-001 | Completed Shipments | MDC | Group 2 | 2022-01-10 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-084411-001 | Supply Commits | MDC | Group 2 | 2022-01-10 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-101870-902 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-101870-902 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-273122-008 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-273122-008 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-334003-001 | Completed Shipments | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-334003-001 | Supply Commits | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
10-143501-00 | Completed Shipments | MDC | Group 2 | 2022-01-13 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-143501-00 | Supply Commits | MDC | Group 2 | 2022-01-13 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-333435-011 | Completed Shipments | MDC | Group 2 | Approved | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-333435-011 | Supply Commits | MDC | Group 2 | Approved | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-323472-005 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-323472-005 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-266070-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-266070-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-323472-002 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-323472-002 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-323472-003 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-323472-003 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-149296-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-149296-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-394919-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-394919-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-445720-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-445720-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-273122-005 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-273122-005 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-290061-008 | Completed Shipments | MDC | Group 2 | TBD | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-290061-008 | Supply Commits | MDC | Group 2 | TBD | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-333435-006 | Completed Shipments | MDC | Group 2 | TBD | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-333435-006 | Supply Commits | MDC | Group 2 | TBD | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-333435-007 | Completed Shipments | MDC | Group 2 | TBD | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-333435-007 | Supply Commits | MDC | Group 2 | TBD | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-145276-07 | Completed Shipments | MDC | Group 2 | 2022-01-11 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
10-145276-07 | Supply Commits | MDC | Group 2 | 2022-01-11 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
10-166680-00 | Completed Shipments | MDC | Group 2 | 2022-01-12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
10-166680-00 | Supply Commits | MDC | Group 2 | 2022-01-12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
839-245596-001 | Completed Shipments | MDC | Group 2 | 2022-01-12 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
839-245596-001 | Supply Commits | MDC | Group 2 | 2022-01-12 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
839-333435-009 | Completed Shipments | MDC | Group 2 | Approved | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
839-333435-009 | Supply Commits | MDC | Group 2 | Approved | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
10-149457-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
10-149457-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
839-308304-001 | Completed Shipments | MDC | Group 2 | 2022-01-13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-308304-001 | Supply Commits | MDC | Group 2 | 2022-01-13 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-317073-001 | Completed Shipments | MDC | Group 2 | Approved | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-317073-001 | Supply Commits | MDC | Group 2 | Approved | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-333435-010 | Completed Shipments | MDC | Group 2 | Approved | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-333435-010 | Supply Commits | MDC | Group 2 | Approved | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-151213-001 | Completed Shipments | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-151213-001 | Supply Commits | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-255648-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-255648-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-143542-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-143542-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-146204-00 | Completed Shipments | MDC | Group 2 | 2022-01-11 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-146204-00 | Supply Commits | MDC | Group 2 | 2022-01-11 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-149847-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-149847-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-149893-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-149893-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-149926-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-149926-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-153142-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-153142-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-156309-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-156309-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-271377-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-271377-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-297760-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-297760-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-440436-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-440436-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-273122-006 | Completed Shipments | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-273122-006 | Supply Commits | MDC | Group 2 | TBD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-276623-003 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
839-276623-003 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
839-290061-003 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-290061-003 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-136163-02 | Completed Shipments | MDC | Group 2 | 2022-01-17 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-136163-02 | Supply Commits | MDC | Group 2 | 2022-01-17 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-143502-00 | Completed Shipments | MDC | Group 2 | 2022-01-13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-143502-00 | Supply Commits | MDC | Group 2 | 2022-01-13 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-145276-06 | Completed Shipments | MDC | Group 2 | 2022-01-11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-145276-06 | Supply Commits | MDC | Group 2 | 2022-01-11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-150114-00 | Completed Shipments | MDC | Group 2 | 2022-01-12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-150114-00 | Supply Commits | MDC | Group 2 | 2022-01-12 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-152277-00 | Completed Shipments | MDC | Group 2 | 2022-01-11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-152277-00 | Supply Commits | MDC | Group 2 | 2022-01-11 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-152731-001 | Completed Shipments | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-152731-001 | Supply Commits | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-181110-002 | Completed Shipments | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-181110-002 | Supply Commits | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-198970-003 | Completed Shipments | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-198970-003 | Supply Commits | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-221767-001 | Completed Shipments | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-221767-001 | Supply Commits | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-229197-001 | Completed Shipments | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-229197-001 | Supply Commits | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-334033-001 | Completed Shipments | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-334033-001 | Supply Commits | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-338158-001 | Completed Shipments | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-338158-001 | Supply Commits | MDC | Group 2 | TBD | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-132464-00 | Completed Shipments | MDC | Group 2 | 2022-01-12 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-132464-00 | Supply Commits | MDC | Group 2 | 2022-01-12 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
853-193770-004 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
853-193770-004 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
02-424910-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-424910-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-342125-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-342125-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-410634-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-410634-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15-431862-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15-431862-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16-421995-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16-421995-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16-421995-00 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16-421995-00 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-004572-155 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-004572-155 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-078004-911 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-078004-911 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-114189-010 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-114189-010 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-179096-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-179096-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-179097-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-179097-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-274183-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-274183-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-274183-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-274183-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-274392-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-274392-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
853-083795-045 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
853-083795-045 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
853-257240-001 | Completed Shipments | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
853-257240-001 | Supply Commits | MDC | Group 2 | TBD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 36 | 129 | 69 | 85 | 285 | 307 | 340 | 220 | 209 | 246 | 1708 | 83 | 44 | 48 | 34 | 35 | 111 | 0 | 2 | 13 | 18 | 118 | 4140
[7 empty] | Part Count: | 88 |  |  |  |  | Part Count: | 25 | [5 empty] | Part Count: | 18
[7 empty] | Unit Count: | 1471 |  |  |  |  | Unit Count: | 2163 | [5 empty] | Unit Count: | 506

## MDC Supply Commits - updated1
PartNumber | Type | Second Supplier | Status | FAIR Completed Date | Past thru 1/23/2022 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | TTL PD-Mar28 | Issues/Notes
839-803173-010 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 120 | 130 | 130 | 130 | 130 | 130 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 905 | Swagelok arriving from MLY 2/7
839-803173-010 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 120 | 130 | 130 | 130 | 130 | 130 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 905 | Swagelok arriving from MLY 2/7
839-078004-111 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863 | Swagelok dates TBD escalated
839-078004-111 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863 | Swagelok dates TBD escalated
839-078004-112 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447 | Swagelok dates TBD escalated
839-078004-112 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447 | Swagelok dates TBD escalated
839-274022-001 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 2 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226
839-274022-001 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 2 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226
839-204868-001 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 30 | 30 | 30 | 30 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 211 | Machined item being expedited (A&T)
839-204868-001 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 30 | 30 | 30 | 30 | 30 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 211 | Machined item being expedited (A&T)
839-084412-799 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 23 | 21 | 26 | 26 | 26 | 26 | 26 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | Partial commit from Hytron, working to improve more
839-084412-799 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 23 | 21 | 26 | 26 | 26 | 26 | 26 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 186 | Partial commit from Hytron, working to improve more
839-204868-003 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 5 | 0 | 0 | 25 | 25 | 25 | 25 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | Aligned upon B2 machining arrival
839-204868-003 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 5 | 0 | 0 | 25 | 25 | 25 | 25 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | Aligned upon B2 machining arrival
839-274019-001 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 122 | HELP, Pricing is wrong, major loss on this part
839-274019-001 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 122 | HELP, Pricing is wrong, major loss on this part
839-802321-001 | Completed Shipments | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96
839-802321-001 | Supply Commits | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96
839-274008-001 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 93
839-274008-001 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 93
10-413657-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74
10-413657-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74
10-418403-00 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 20 | 20 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | Aligned in Q1
10-418403-00 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 20 | 20 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | Aligned in Q1
839-173298-003 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 5 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
839-173298-003 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 5 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
839-290061-002 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 30 | Aligned in Q1
839-290061-002 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 30 | Aligned in Q1
839-239359-003 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
839-239359-003 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
839-274148-001 | Completed Shipments | MDC | Group 2 |  | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
839-274148-001 | Supply Commits | MDC | Group 2 |  | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
839-179101-002 | Completed Shipments | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
839-179101-002 | Supply Commits | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
10-422851-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-422851-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-422993-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-422993-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-422994-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-422994-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-423531-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-423531-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-434785-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
10-434785-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
839-274027-001 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
839-274027-001 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
839-285733-005 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
839-285733-005 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21
839-155217-002 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
839-155217-002 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
10-374386-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
10-374386-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
10-296855-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
10-296855-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19
853-A05403-004 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 18
853-A05403-004 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 18
839-276623-001 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 15
839-276623-001 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 15
839-273816-001 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-273816-001 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-276623-002 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 13
839-276623-002 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 13
10-271948-00 | Completed Shipments | MDC | Group 2 |  | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
10-271948-00 | Supply Commits | MDC | Group 2 |  | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-273153-001 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-273153-001 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-273153-002 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-273153-002 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
839-153177-001 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 12
839-153177-001 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 12
839-272464-001 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
839-272464-001 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
10-283365-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
10-283365-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
839-229542-002 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
839-229542-002 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
839-290061-004 | Completed Shipments | MDC | Group 2 |  | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
839-290061-004 | Supply Commits | MDC | Group 2 |  | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
10-297758-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
10-297758-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
839-330146-003 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
839-330146-003 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
10-271203-00 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
10-271203-00 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
839-298117-001 | Completed Shipments | MDC | Group 2 |  | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
839-298117-001 | Supply Commits | MDC | Group 2 |  | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
839-298118-001 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
839-298118-001 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
10-430901-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6
10-430901-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6
839-333435-008 | Completed Shipments | MDC | Group 2 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
839-333435-008 | Supply Commits | MDC | Group 2 |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
857-223231-001 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
857-223231-001 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
19-047653-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
19-047653-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-068732-006 | Completed Shipments | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-068732-006 | Supply Commits | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-069366-808 | Completed Shipments | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-069366-808 | Supply Commits | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-084411-001 | Completed Shipments | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-084411-001 | Supply Commits | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-101870-902 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-101870-902 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-273122-008 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-273122-008 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-334003-001 | Completed Shipments | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
839-334003-001 | Supply Commits | MDC | Group 2 |  | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
10-143501-00 | Completed Shipments | MDC | Group 2 |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-143501-00 | Supply Commits | MDC | Group 2 |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-333435-011 | Completed Shipments | MDC | Group 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-333435-011 | Supply Commits | MDC | Group 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-323472-005 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-323472-005 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-266070-00 | Completed Shipments | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-266070-00 | Supply Commits | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-323472-002 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-323472-002 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-323472-003 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-323472-003 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-149296-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-149296-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-394919-00 | Completed Shipments | MDC | Group 2 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-394919-00 | Supply Commits | MDC | Group 2 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-445720-00 | Completed Shipments | MDC | Group 2 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-445720-00 | Supply Commits | MDC | Group 2 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-273122-005 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-273122-005 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-290061-008 | Completed Shipments | MDC | Group 2 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-290061-008 | Supply Commits | MDC | Group 2 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-333435-006 | Completed Shipments | MDC | Group 2 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-333435-006 | Supply Commits | MDC | Group 2 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-333435-007 | Completed Shipments | MDC | Group 2 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
839-333435-007 | Supply Commits | MDC | Group 2 |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
10-145276-07 | Completed Shipments | MDC | Group 2 |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
10-145276-07 | Supply Commits | MDC | Group 2 |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
10-166680-00 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
10-166680-00 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
839-245596-001 | Completed Shipments | MDC | Group 2 |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
839-245596-001 | Supply Commits | MDC | Group 2 |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
839-333435-009 | Completed Shipments | MDC | Group 2 |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
839-333435-009 | Supply Commits | MDC | Group 2 |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
10-149457-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
10-149457-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
839-308304-001 | Completed Shipments | MDC | Group 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-308304-001 | Supply Commits | MDC | Group 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-317073-001 | Completed Shipments | MDC | Group 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-317073-001 | Supply Commits | MDC | Group 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-333435-010 | Completed Shipments | MDC | Group 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-333435-010 | Supply Commits | MDC | Group 2 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-151213-001 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-151213-001 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-255648-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-255648-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-143542-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-143542-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-146204-00 | Completed Shipments | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-146204-00 | Supply Commits | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-149847-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-149847-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-149893-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-149893-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-149926-00 | Completed Shipments | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-149926-00 | Supply Commits | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-153142-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-153142-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-156309-00 | Completed Shipments | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-156309-00 | Supply Commits | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-271377-00 | Completed Shipments | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-271377-00 | Supply Commits | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-297760-00 | Completed Shipments | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-297760-00 | Supply Commits | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-440436-00 | Completed Shipments | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-440436-00 | Supply Commits | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-273122-006 | Completed Shipments | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-273122-006 | Supply Commits | MDC | Group 2 |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-276623-003 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
839-276623-003 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2
839-290061-003 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
839-290061-003 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
10-136163-02 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-136163-02 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-143502-00 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-143502-00 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-145276-06 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-145276-06 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-150114-00 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-150114-00 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-152277-00 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-152277-00 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-152731-001 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-152731-001 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-181110-002 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-181110-002 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-198970-003 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-198970-003 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-221767-001 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-221767-001 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-229197-001 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-229197-001 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-334033-001 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-334033-001 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-338158-001 | Completed Shipments | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
839-338158-001 | Supply Commits | MDC | Group 2 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-132464-00 | Completed Shipments | MDC | Group 2 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
10-132464-00 | Supply Commits | MDC | Group 2 |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
853-193770-004 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
853-193770-004 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
02-424910-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
02-424910-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-342125-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-342125-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-410634-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10-410634-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15-431862-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15-431862-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16-421995-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16-421995-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16-421995-00 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16-421995-00 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-004572-155 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-004572-155 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-078004-911 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-078004-911 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-114189-010 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-114189-010 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-179096-001 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-179096-001 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-179097-001 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-179097-001 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-274183-001 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-274183-001 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-274183-001 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-274183-001 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-274392-001 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
839-274392-001 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
853-083795-045 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
853-083795-045 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
853-257240-001 | Completed Shipments | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
853-257240-001 | Supply Commits | MDC | Group 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Part Count: | 88 |  |  |  |  | Part Count: | 25 | [5 empty] | Part Count: | 18
[7 empty] | Unit Count: | [5 empty] | Unit Count: | 2163 | [5 empty] | Unit Count: | 506